## Sheet1
Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | Date of Receipt of Valid Research Application | Date of First Patient Recruited | Benchmark Met | Reasons for delay correspond to:
12/EE/0368 | 106851 | A randomised blinded placebo controlled trial of hydrocortisone in critically ill patients with septic shock. ADRENAL Study - Adjunctive coRticosteroid trEatment iN criticAlly ilL patients with septic shock | 2015-06-23 | 2015-08-05 | Yes
13/LO/1557 | 135995 | CALM-NET: A Phase IV, Multicentre, Open Label, Single Group Exploratory Study to Assess the Clinical Value of Enumeration of Circulating Tumour Cells (CTCs) to Predict Clinical Symptomatic Response and Progression Survival in Patients Receiving Deep Subcu | 2015-04-22 | 2015-06-23 | Yes
13/SC/0309 | 128504 | A Phase Ib Study of Eltrombopag and Azacitidine in Patients with High Risk Myelodysplastic Syndromes and Related Disorders (ELASTIC) | 2015-04-02 |  | No | Sponsor
13/YH/0279 | 122908 | Pain Reduction with Oral Methotrexate in Knee Osteoarthritis, a pragmatic phase III trial of Treatment Effectiveness | 2015-06-02 | 2015-07-21 | Yes
14/EE/0152 | 148007 | A Phase III, case series clinical study of the reversal of the anticoagulant effects of dabigatran by intravenous administration of 5.0g idarucizumab (BI 655075) in patients treated with dabigatran etexilate who have uncontrolled bleeding or require emerg | 2015-04-27 |  | No | Sponsor
14/EE/0204 | 151441 | Hydrotherapy for Duchenne muscular dystorphy (DMD): a pilot and feasibility randomised controlled trial in children | 2015-04-13 | 2015-05-29 | Yes
14/EE/1224 | 158485 | A Phase 2b Open-label, Randomized Two-arm Study of Selinexor (KPT-330) with Low Dose Dexamethasone in Patients with Relapsed/Refractory Diffuse Large B-Cell Lymphoma (DLBCL) | 2015-04-29 | 2015-07-22 | No | Sponsor
14/LO/0673 | 146391 | A phase 3, randomised, placebo controlled, double-blind study of oral Ixazomib Citrate (MLN9708) maintenance therapy in patients with mulitple myeloma following autologus stem cell transplant | 2015-04-13 | 2015-10-13 | No | Sponsor
14/LO/0871 | 136586 | A randomized controlled trial of a duodenal sleeve bypass device (EndoBarrier) compared with standard medical therapy for the management of obese subjects with type 2 diabetes | 2015-06-02 | 2015-07-03 | Yes
14/LO/1279 | 150015 | RCT of azithromycin maintenance therapy in Primary Ciliary Dyskinesia | 2015-04-14 | 2015-05-27 | Yes
14/LO/1798 | 161154 | GO29294 AntiPDL1 Bladder Cancer Phase III | 2015-04-29 | 2015-06-24 | Yes
14/LO/2218 | 161762 | Randomised phase 3 trial of enzalutamide in first line androgen deprivation therapy for metastatic prostate cancer: ENZAMET | 2015-06-18 | 2015-10-28 | No | Sponsor
14/NE/0011 | 138347 | STRIDER: A Randomised Controlled Trial of Sildenafil Therapy InDismal Prognosis Early-Onset Intrauterine Growth Restriction | 2015-05-15 | 2015-11-05 | No | Sponsor
14/NE/0155 | 151842 | SURAB Study - A randomised study comparing abalation with active surveillance, in the management of incidentially diagnosed small renal tumours: a feasibility study | 2015-05-07 |  | No | Sponsor
14/NE/1099 | 144103 | Phase III, randomised, multicenter, double-blind, double-dummy study to evaluate the efficacy and safety of Etrolizumab compared with Infliximab in patients with moderate to severe active ulcerative colitis who are naive to TNF inhibitors. | 2015-06-23 | 2015-09-17 | No | Neither
14/NE/1253 | 168678 | A Phase I, Open-Label, Non-Randomised, Multicentre Study to Assess the Effect of AZD9291 on the Pharmacokinetics of Rosuvastatin (a Sensitive BCRP Substrate) in Patients with EGFRm Positive NSCLC whose disease has Progressed on an EGFR TKI | 2015-04-16 |  | No | Neither
14/NW/1036 | 152581 | A multicenter, open-label, phase 2 study of S-588410 as maintenance monotherapy after first-line plantinum-containing chemotherapy in patients with advanced and/or metastatic bladder cancer | 2015-03-18 |  | No | Neither
14/SC/1032 | 142646 | Dietary Management of Adult Eosinophilic Oesophagitis: The efficacy of an elemental + few foods diet vs. six food elimination diet in inducing remission in adult patients with Eosinophilic Oesophagitis. | 2015-05-06 | 2015-08-28 | No | Neither
14/SC/1346 | 151280 | National Lung Matrix: Multi-drug, genetic marker-directed, non-comparative,mulit-centre, multi-arm, phase II trial in non-small cell lung cancer | 2015-04-21 | 2015-10-07 | No | Sponsor
14/WM/1145 | 161184 | An international, multicentre, efficacy and safety study of I10E in initial and maintenance treatment of patients with Chronic Inflammatory Demyelinating Polyradiculoneuropayhy. | 2015-05-01 | 2015-08-03 | No | Neither
14/WS/1106 | 157143 | A Comparison of Fractional Flow Reserve-Guided Percutaneous Coronary Intervention and Coronary Artery Bypass Graft Surgery in Patients with Multivessel Coronary Artery Disease: Fractional Flow Reserve versus Angiography for Multivessel Evaluation (FAME) 3 | 2015-06-04 | 2015-09-23 | No | Neither
14/YH/1263 | 162807 | GLYSURE Study | 2015-04-13 | 2015-06-10 | Yes
15/LO/0402 | 171363 | A Phase 2b, Randomized, Double-Blind, Placebo-Controlled Study to Evaluate the Safety and Efficacy of Staphylococcus Aureus-4-Antigen Vaccine (SA4Ag) in Adults Undergoing Elective Posterior Instrumented Lumbar Spinal Fusion Procedures | 2015-06-23 | 2015-11-04 | No | Neither
15/SC/0065 | 154166 | A Phase III, Open-label, Randomised, Multi-centre, International Study of MEDI4736, Given as Monotherapy or in Combination with Tremelimumab, Determined by PD-L1 Expression, Versus Standard of Care in Patients with Locally Advanced or Metastatic Non-Small | 2015-05-28 | 2015-09-10 | No | Neither
15/YH/0005 | 166291 | A Phase 3 Confirmatory Study Investiginating the Efficacy and Safety of Dupilumab Monotherapy Administered to Adult Patients with Moderate-to-severe Atopic Dermatitis | 2015-05-05 |  | No | Sponsor
15/YH/0125 | 165426 | An Open-Label, Phase 1b/2 Study of ACP-196 in subjects with Waldenstrom Macroglobulinemia | 2015-06-08 | 2015-07-29 | Yes
10/H0405/90 | 50787 | A randomised controlled trial of eicosapentaenoic acid (EPA) and/or aspirin for colorectal adenoma (or polyp) prevention during colonoscopic surveillance in the NHS Bowel Cancer Screening Programme: The seAFOod (Systematic Evaluation of Aspirin and Fish O | 2015-08-24 |  | No | Sponsor
11/H1102/8 | 50714 | A multicentre, prospective, single arm intervention trial evaluating focal therapy using high intensity focused ultrasound (Sonablate 500) for localised prostate cancer | 2015-09-09 | 2015-10-29 | Yes
13/EM/0078 | 120878 | The Role of Glasses Wearing in Amblyopia Treatment A Randomised Controlled Multicentre Trial | 2015-09-01 | 2015-11-24 | No | Neither
13/LO/0108 | 112000 | A Randomised Phase II Study Comparing Lenalidomide plus Rituximab, Gemcitabine and Methylprednisolone (L-RGEM) to Ritixumab, Gemcitabine, Methylprednisolone and Cisplatin (RGEMP) in Second Line Treatment of Diffuse Large B-cell Lyphoma (DLBCL) (LEGEND) | 2015-09-28 |  | No | Neither
13/NE/0196 | 125526 | Antibiotic treatment for intermittent bladder catheterisation: A randomised controlled trial of once daily prophylaxis (The AnTIC study) | 2015-08-25 |  | No | Neither
13/SC/0421 | 134950 | A Phase 1, randomized, blinded, dose-escalation study of rAAV1-PG9DP recombinant AAV vector coding for PG9 antibody in healthy male adults. | 2015-09-14 |  | No | Sponsor
13/WA/0205 | 127379 | An Open-Label, Multicenter, Phase 1/2 Study of E7438 (EZH2 Histone Methyl Transferase [HMT] Inhibitor) as a Single Agent in Subjects with Advanced Solid Tumors or With B cell Lymphomas | 2015-07-21 | 2015-09-11 | Yes
14/LO/0056 | 129966 | Phase III, pivotal, multicentre, randomised, double-blind, controlled study to evaluate the efficacy and safety of autologous osteoblastic Cells (PREOB ® ) implantation in early stage non traumatic osteonecrosis of the femoral head. (PREO®-ON3) | 2015-07-31 |  | No | Neither
14/LO/2119 | 160335 | A multicentre, randomised, clinical trial of biomarker-driven maintenance treatment for first line metastatic colorectcal cancer (MODUL) | 2015-07-23 | 2015-10-28 | No | Neither
14/NE/1041 | 156574 | A double-blind, randomized, placebo-controlled cross over study of inhaled alginate oligosaccharide (OligoG) administered for 28 days in subjects with Cystic Fibrosis | 2015-07-21 | 2015-09-23 | Yes
14/NE/1063 | 144094 | Phase III, Double Blind, Placebo-controlled, Multicenter Study of the Efficacy and Safety of Etrolizumab During Induction and Maintenance in Patients with Moderate to Severe Active Ulcerative Colitis who are Refractory to or Intolerant of TNF Inhibitors | 2015-06-23 | 2016-01-08 | No | Sponsor
14/NI/1120 | 149397 | EDNA: Early Detection of Neovascular Age-related macular degeneration (AMD) | 2015-08-03 | 2015-10-19 | No | Sponsor
14/NW/0001 | 138498 | A Phase 3b Continuation study of the Safety and Efficacy of PEGylated Recombinant Factor VIII (PEG-rFVIII; BAX 855) in Prophylaxis of Bleeding in Previously Treated Patients with Severe Hemophilia A | 2015-09-29 | 2015-10-12 | Yes
14/SC/0184 | 150048 | An open-label, multicenter, extension study to evaluate the long-term safety of subcutaneous 240mg QGE031 given every 4 weeks for 52 weeks in allergic asthma patients who completed study CQGE031B2201 | 2015-07-02 | 2015-07-31 | Yes
14/SC/0221 | 145869 | A randomised phase II pilot study of 3 weekly Cabazitaxel versus weekly Paclitaxel chemotherapy in the first line treatment of HER2 negative metastatic breast cancer | 2015-09-01 |  | No | Neither
14/SC/0237 | 153330 | A randomised controlled trial to determine the clinical and cost effectiveness of invasive urodynamic studies for diagnosis and management of bladder outlet obstruction in men in the National Health Service (NHS) | 2015-07-02 | 2015-07-24 | Yes
14/WM/1241 | 168143 | Refining Ovarian Cancer Test Accuracy Scores: A test accuracy study to validate new risk scores in women with symptoms of suspected ovarian cancer protocol (ROCkeTS study) | 2015-09-01 | 2015-09-30 | Yes
14/WS/1014 | 147250 | Wave IV Study: Phase II Randomized Sham Controlled Study of Renal Denervation for Subjects with Uncontrolled Hypertension | 2015-06-30 |  | No | Sponsor
14/YH/0128 | 150031 | Sacral nerve stimulation versus the FENIX magnetic sphincter augmentation for adult faecal incontinence: a Randomised Investigation (SaFaRI) | 2015-06-30 | 2015-07-07 | Yes
14/YH/1278 | 166264 | Validation of the TEG 6s device for assessment of individual responses to antiplatelet therapy in ischaemic heart disease using the TEG 5000 series as a reference | 2015-07-07 | 2015-07-21 | Yes
15/EM/0069 | 162273 | A prospective, open label, multicentre randomized phase III trial to compare the efficacy and safey of a combined regimen of Obinutuzumab and GDC-0199 (ABT-199) versus Obinutuzumab and Chlorambucil in previously untreated patients with CLL and co-existing | 2015-07-15 | 2015-10-19 | No | Neither
15/EM/0300 | 180135 | A Phase III, Open Lable, Multicentre, Randomized Study of MPDL3280A (Anti-PD-L1 Antibody) versus Observation as Adjuvant Therapy in Patients with PD-L1 Positive, High Risk Muscle-Invasive Bladder Cancer After Cystectomy | 2015-09-01 | 2015-12-23 | No | Neither
15/LO/0034 | 169816 | OPuS-2: A Multicenter, Randomized, Double-Blind, Placebo-Controlled, Parallel Group Study to Evaluate the Efficacy and Safety of Two Dose Levels of BCX4161 for 12 weeks as an Oral Phophylaxis Treatment for Attacks of Hereditary Angioedema | 2015-07-22 | 2015-08-21 | Yes
15/LO/0691 | 174324 | An Open-Label, Multicenter Clinical Trial with Nivolumab (BMS-936558) Monotherapy in Subjects with Advanced or Metastatic Squamous Cell (Sq) Non-Small Cell Lung Cancer (NSCLC) who Have Received at Least Two Prior Systemic Regimens for the Treatment of Sta | 2015-09-01 | 2015-11-30 | No | Neither
15/LO/0897 | 171318 | A phase III, open-label, randomized study of MPDL3280A (Anti-PD-L1 antibody) in combination with bevacizumab versus sunitinib in patients with untreated advanced renal cell carcinoma | 2015-09-01 | 2015-10-23 | Yes
15/LO/1006 | 174724 | An open-label, single-arm Phase II study in patients with relapsed or refractory diffuse large B-cell lymphoma (DLBCL) to evaluate efficacy and safety of treatment with single agent copanlisib and the impact of biomarkers thereupon | 2015-09-01 | 2015-11-16 | No | Neither
15/NE/0087 | 166519 | Immune responses to bacterial components in patients convalescing from bacteraemia/sepsis caused by pathogenic Escherichia coli | 2015-08-05 | 2015-08-18 | Yes
15/NW/0004 | 162679 | A multicentre, randomised, clinical trial of biomarker-driven maintenance treatment for first line metastatic colorectal cancer | 2015-07-23 | 2015-09-30 | Yes
15/NW/0051 | 183489 | Improving Teenager Self-Management of Asthma (ITSMyAsthma) | 2015-07-01 | 2015-08-13 | Yes
15/NW/0664 | 186961 | Role of the Basophil Activation Test (BAT) for defining further investigation in peri-operative anaphylaxis | 2015-09-08 |  | No | Neither
15/SC/0003 | 154916 | A phase III randomised, double-blind, placebo-controlled clinical trial of BBI608 plus weekly paclitaxel vs placebo plus weekly paclitaxel in adult patients with advanced, previously treated gastric and gastro-esophageal junction adenocarcinoma | 2015-07-30 | 2015-10-21 | No | Neither
15/SC/0054 | 171682 | A Phase 3, Randomised, Double-blind Study of Adjuvant Immunotherapy with Nivolumab verus Impilimumab after Complete Resection of Stage IIIb/c Stage IV Melanoma in Subjects who are at High Risk for Recurrence (CheckMate 238) | 2015-06-30 | 2015-07-30 | Yes
15/SC/0142 | 172958 | NUTRITIONAL INTERVENTION PRECONCEPTION AND DURING PREGNANCY TO MAINTAIN HEALTHY GLUCOSE METABOLISM AND OFFSPRING HEALTH | 2015-07-24 | 2015-08-14 | Yes
15/SC/0237 | 179459 | A phase Ia clinical trial to assess the safety, immunogenicity and ex-vivo efficacy of new Plasmodium falciparum malaria vaccine candidates ChAd63 Pfs-IMX313 alone and with MVA Pfs25-IMX313 | 2015-09-10 | 2015-09-21 | Yes
15/SC/0256 | 177204 | A randomized, double-blind, placebo-controlled, parallel group, multi-centre Phase IIa study in asthma patients comparing the efficacy and safety of once daily inhaled Interferon beta-1a to placebo, administered for 14 days after the onset of symptoms of | 2015-08-04 | 2015-11-16 | No | Neither
15/SC/0291 | 173738 | An open label, multicohort, phase II study of MPDL3280A in advanced solid tumours | 2015-09-01 | 2015-10-01 | Yes
15/LO/1233 | 118442 | A comparison of body composition techniques in COPD patients (COBOCO) | 2015-08-26 | 2015-09-15 | Yes
15/SW/0086 | 165595 | A Phase 3 Study Comparing Daratumumab, Lenalidomide, and Dexamethasone (DRd) vs Lenalidomide and Dexamethasone (Rd) In Subjects with Previously Untreated Multiple Myeloma who are Ineligible for High Dose Therapy | 2015-08-06 | 2015-11-10 | No | Neither
15/WM/0102 | 172463 | A Randomized Phase 2 Trial of Evaluate Three Daratumumab Dose Schedule in Smoldering Multiple Myeloma | 2015-08-20 |  | No | Neither
15/EM/0135 | 167922 | An Open-label, Phase 2 Study of ACP-196 in Subjects with Mantle Cell Lymphoma | 2015-07-27 | 2015-08-21 | Yes
15/YH/0178 | 174447 | A Phase 3, Randomized, DoubleBlined, ivacaftorControlled, ParallelGroup Study to Evaluate the Efficacy and Safety of VX661 in Combination With Ivacaftor in Subjects Aged 12 years and Older With Cystic Fibrosis, Heterozygous for the F508delCFTR Mutation an | 2015-09-01 | 2015-11-04 | Yes
13/EM/0462 | 136755 | Phase I/II study to determine the maximum tolerated dose and activity of the combination of romidepsin and carfilzomib in relapsed or refractory peripheral T-cell lymphoma (RomiCar) | 2015-10-07 |  | No | Neither
13/LO/1401 | 128104 | Focal RECurrent Assessment and Salvage Treatment: FORECAST | 2015-10-19 | 2015-10-28 | Yes
13/NE/0339 | 131556 | GOT-IT Trial: A pragmatic group sequential placebo controlled randomised trial to determine the effectiveness of Glyceryl trinitrate for retained placenta | 2015-11-09 | 2015-11-28 | Yes
13/NS/0155 | 139913 | A multicentre randomised controlled trial comparing laparoscopic supra-cervical hysterectomy with second generation endometrial ablation for the treatment of heavy menstrual bleeding (HEALTH) | 2015-09-30 | 2015-10-27 | Yes
13/SC/0436 | 108256 | Early Low Dose Steroids for Adults Admitted to Hospital with Influenza-like Illness During a Pandemic: A Randomised Placebo Controlled Trial (ASAP) | 2015-10-12 |  | No | Neither
14/NW/0176 | 148100 | A Prospective, Randomized, Controlled Study Evaluating EVICEL® Fibrin Sealant as an Adjunct to Haemostasis During Abdominal, Retroperitoneal, Pelvic or Thoracic (Non-Cardiac) Surgery in Paediatric Patients | 2015-12-07 |  | No | Neither
14/LO/1206 | 154429 | Planning treatment for oesophago-gastric cancer: a randomised maintenance therapy trial (PLATFORM) Trial | 2015-10-22 |  | No | Neither
14/LO/1578 | 156798 | A phase II randomized and controlled investigation of six weeks or oral valganciclovir therapy in infants and children with congenital cytomegalovirus infection and hearing loss | 2015-11-23 | 2016-02-10 | No | Neither
14/LO/1611 | 139000 | COOK IVC Filter Study | 2015-10-22 |  | No | Sponsor
14/LO/2219 | 163775 | Randomised phase 3 trial of enzalutamide in first line androgen deprivation therapy with radiation therapy for high risk, clinically localised, prostate cancer: ENZARAD | 2015-11-25 |  | No | Neither
14/NE/1018 | 150960 | A Randomised, Double-blind, Chronic Dosing (56 week) Placebo-controlled, Parallel Group, Multicentre, Phase III Study to Evaluate the Efficacy and Safety of 2 Doses of Benralizumab (MEDI-563) in Patients with Moderate to Very Severe Chronic Obstructive Pu | 2015-11-30 | 2016-02-03 | Yes
14/NE/1062 | 140391 | PHOTOdynamic versus white light-guided treatment of non-muscle invasive bladder cancer: randomised trial of clinical and cost-effectiveness | 2015-09-30 | 2015-11-04 | Yes
14/NE/1100 | 152481 | Surveillance of Children and Young Adults Following Neuro-oncology Treatment to Assess Prevalence and Nature of Sleep Problems | 2015-12-14 | 2016-03-17 | No | Neither
13/LO/0706 | 119677 | UK Multicentre Study of Children Opsoclonus Myoclonus Symdrome (UMSCOM) | 2015-12-07 |  | No | Neither
14/SC/0171 | 120104 | A phase III, double-blind, placebo-controlled, randomised trial assessing the effects of aspirin on disease recurrence and survival after primary therapy in common non-metastatic solid tumours | 2015-11-24 |  | No | Sponsor
14/SC/1376 | 159568 | PART A - A randomised controlled trial of Partial prostate Ablation versus Radical prosTatectomy (PART) in intermediate risk, unilaterial clinically localised prostate cancer | 2015-10-06 | 2015-12-16 | Yes | Neither
14/SC/1377 | 152728 | An Exploratory Investigation into the Use of the Milk Ladder in Children With IgE Mediated Cow's Milk Allergy (CMA) in the UK | 2015-09-14 |  | No | Sponsor
14/SS/1096 | 164274 | The role of early CT Coronary Angiography in the evaluation, intervention and outcome of patients presenting to the Emergency Department with suspected or confirmed Acute Coronary Syndrome | 2015-09-30 | 2015-10-28 | Yes
14/WA/1118 | 159836 | A Phase II/III trial of risk-stratified, reduced intensity adjuvant treatment in patients undergoing transoral surgery for Human papillomavirus (HPV)-positive oropharyngeal cancer | 2015-10-29 |  | No | Neither
14/WM/1235 | 164908 | International, multicentre, efficacy and safety study of I10E in the maintenance treatment of patients with Chronic Inflammatory Demyelinating Polyradiculoneuropathy: Extension of PRISM study I10E-1302 | 2015-12-01 | 2016-02-02 | Yes
14/WS/1021 | 155214 | PHASE 3 EFFICACY AND SAFETY STUDY OF ATALUREN (PTC124®) IN PATIENTS WITH NONSENSE MUTATION CYSTIC FIBROSIS | 2015-10-09 |  | No | Sponsor
14/WS/1107 | 126320 | Pertuzumab + trastuzumab (PH) versus PH plus metronomic chemotherapy (PHM) in the elderly HER2+ metastatic breast cancer population who may continue on T-DM1 alone following disease progression while on PH / PHM: an open-label multicentre randomized phase | 2015-11-24 |  | No | Neither
15/EE/0370 | 189865 | Efficacy and safety of semaglutide versus dulaglutide as add-on to metformin in subjects with type 2 diabetes - SUSTAIN-7 | 2015-12-17 | 2016-02-17 | Yes
15/LO/0443 | 172123 | A phase 3, multicenter, randomized, open-label study to compare the efficacy and safety of pomalidomide , bortezomid and low-dose dexamethasone verus bortezomib and low-dose dexamethasone in subjects with relapsed or refractory mutliple myeloma | 2015-11-26 |  | No | Neither
15/LO/0564 | 173148 | ARMOR3-SV - A phase 3, randomised, open label, multicentre, controlled study of galeterone compared to enzalutamide in men expressing androgen receptor splice variant 7 mRNA (AR-V7) metastatic (M1) castrate resistant prostate cancer (CRPC) | 2015-10-26 | 2015-12-16 | Yes
15/LO/0771 | 179095 | APTITUDE A phase II trial of Tocilizumab in anti-TNF refractory patients with JIA associated uveitis. | 2015-11-11 |  | No | Neither
15/LO/1074 | 182401 | A multi-centre, randomized, placebo-controlled, double blinded, multiple dose trial investigating safety, pharmacokinetics of concizumab administered subcutaneously to haemophilia A subjects (Explorer 3) | 2015-10-13 |  | No | Neither
15/LO/1664 | 189065 | A Case Control Study of the Effectiveness of Q/LAIV Versus Inactivated Influenza Vaccine and No Vaccine in Subjects 2-17 years of age (ICICLE) | 2015-11-12 | 2016-01-19 | Yes
15/NE/0143 | 174391 | A phase III, randomized, double-blind, placebo-controlled, multicenter study to evaluate the efficacy and safety of etrolizumab as an induction and maintenance treatment for patients with moderately to severely active crohn’s disease | 2015-10-22 | 2016-02-12 | No | Neither
15/SC/0522 | 155603 | Investigating the impact of a short-course MBSR-based mindfulness intervention on patients with difficult-to-manage asthma | 2015-12-02 | 2016-01-13 | Yes
15/NE/0278 | 183395 | An open-label, randomized, active-controlled, parallel-group, Phase-3b study of the efficacy, safety, and tolerability of 2mg aflibercept administered by intravitreal injections using two different treatment regimens to subjects with neovascular age-relat | 2015-11-06 |  | No | Neither
15/NI/0158 | 182421 | A Randomised Pragmatic Trial of Corticosteroid Optimisation in Severe Asthma Using a Composite Biomarker Algorithm to Adjust Corticosteroid Dose Versus Standard Care | 2015-12-22 | 2016-02-26 | Yes
14/EM/0084 | 144316 | A Prospective, Randomised, Controlled, Study Evaluating the Safety and Effectiveness of EVARREST™ Sealent Matrix in Controlling Mild or Moderate Hepatic Parenchyma of Soft Tissue Bleeding During Open Abdominal, Retroperitoneal, Pelvic and Thoracic (non-ca | 2015-12-07 |  | No | Neither
15/NW/0171 | 168748 | A randomised, double blind, placebo-controlled trial of a two-week course of dexamethasone for adult patients with a symptomatic Chronic Subdural Haematoma (Dex-CSDH trial) | 2015-12-15 | 2016-01-29 | Yes
15/NW/0416 | 167060 | A randomised phase II trial of Cyclophosphamide and Dexamethasone in combination with Ixazomib, in relapsed or refractory multiple myeloma (RRMM) patients who have relapsed after treatment with thalidomide, lenalidomide and bortezomib | 2015-11-10 |  | No | Neither
15/NW/0430 | 178084 | A Multicenter Study of Patients treated with the Ellipse Technologies Intramedullary High Tibial Osteotomy (IM HTO) Nail System for Osteoarthritis and Varus Malalignment of the Knee | 2015-11-02 | 2016-02-01 | No | Neither
15/NW/0468 | 182025 | A Randomized, Multicenter, Open-Label, 3 Arm Phase 3 Study of Obinuzumab in Combination with Chlorambucil, ACP-196 in Combination with Obinutuzumab, and ACP-196 Monotherapy in Subjects with Previously Untreated Chronic Lymphocytic Leukemia | 2015-10-08 |  | No | Neither
15/NW/0492 | 181246 | A Randomized, Mulitcenter, Open-Label, Non-Inferiority, Phase 3 Study of ACP-196 Versus Ibrutinib in Previously Treated Subjects with High Risk Chronic Lymphocyitic Leukemia | 2015-10-08 | 2016-01-25 | No | Neither
15/NW/0631 | 185354 | A phase III, double blind, randomized, comparative study of the safety and immunogenicity of GSK Biologicals' Varilrix HSA-free varicella vaccine and Varilrix™ given as a 2 dose course in the second year of life | 2015-11-24 | 2016-01-11 | Yes
15/NW/0699 | 185674 | ABT-493/ABT-530 - Phase III - A Randomized, Open-Label, Multicenter Study to Evaluate the Efficacy and Safety of ABT-493/ABT-530 in Adults with Chronic Hepatitis C Virus Genotype 1 Infection (ENDURANCE-1) | 2015-11-27 | 2015-12-23 | Yes
15/SC/0213 | 170160 | A Multicenter, Randomized, Double-Blind, Placebo-Controlled Study of ABT-494 for the Induction of Symptomatic and Endoscopic Remission in Subjects with Moderately to Severely Active Crohn's Disease who have Inadequately Responded to or are Intolerant to A | 2015-11-05 | 2015-11-17 | Yes
15/SC/0289 | 180375 | A Cancer Research UK Randomised, Double-blind, Placebo-controlled Phase Iia trial of AMG-319 given orally as a neoadjuvant therapy in patients with human papillomavirus (HPV) negative head and neck squamous cell carcinoma (HNSCC) | 2015-11-19 |  | No | Neither
15/SC/0311 | 181166 | Impact of bystander disease after primary PCI to the culprit vessel after STEMI: prevalence of ischaemia and incidence of clinical events | 2015-12-10 | 2015-12-16 | Yes
15/SC/0528 | 188192 | Microbiology and Immunology of the Chronically-inflamed Airway (MICA) II | 2015-10-02 | 2015-10-08 | Yes
15/SC/0573 | 188609 | An open-label extension and safety monitoring study of moderate to severe ulcerative colitis patients previously enrolled in Etrolizumab phase III studies. | 2015-11-26 | 2016-01-18 | Yes
15/WA/0277 | 167056 | Corneal Imaging in Children | 2015-10-07 | 2015-11-02 | Yes
15/WA/0302 | 183559 | Study of mechanisms of action of Omalizumab in Severe Asthma (SoMOSA) | 2015-10-26 | 2015-12-09 | Yes
15/WM/0036 | 161768 | A multi-centre randomised controlled trial of the efficacy and mechanism of action of gabapentin for the management of chronic pelvic pain in women (GaPP2 2) | 2015-12-15 | 2016-01-28 | Yes
15/WS/0011 | 122822 | A Trial to Evaluate the Potential Benefit of Adjuvant Chemotherapy for Small Bowel Adenocarcinoma (IRCI-002) - BALLAD | 2015-10-28 |  | No | Neither
15/WS/0153 | 184667 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study Evaluating the Efficacy and Safety of a Human Monoclonal Antibody, REGN2222, for the Prevention of Medically Attended RSV Infection in Preterm Infants | 2015-11-25 | 2016-01-07 | Yes
15/WS/0216 | 189003 | Phase 3, prospective, multi-center, open label study to investigate safety, immunogenicity, and hemostatic efficacy of PEGylated Factor VIII (BAX 855) in previously untreated pateints (PUPs) and minimally treted patients (MTPs) ,6 years with severe hemophilia A | 2015-11-19 |  | No | Neither
15/YH/0020 | 164086 | CALiBRe: Assessment of the Mechanism of Action idelalisib (CAL-101) in B-cell Receptor Pathway Inhibition in CLL | 2015-11-10 |  | No | Neither
12/EE/0127 | 97213 | A Randomised, Double-Blind, Placebo-Controlled, Single Ascending Dose Group Study to Assess the Safety, Tolerability, Pharmacokinetics, Efficacy and Pharmacodynamics of A single Intravenous Administration of KBSA301 in Severe Pneumonia Caused by Staphyloc | 2016-01-04 |  | No
13/LO/0968 | 98339 | RECITAL | 2016-03-04 |  | N/A
13/LO/1595 | 136836 | CBT vs Standardised Medical Care to treat Dissociative Seizures (CODES) | 2016-02-16 | 2016-03-29 | Yes
14/EM/1284 | 159662 | Neo-AEGIS (NEOadjuvant trial in Adenocarcinoma of the oEsophagus and oesophagoGastric junction International Study): Randomised Clinical Trial of neodjuvant and adjuvant chemotherapy (Modified MAGIC regimen) vs. Neoadjuvant chemoradiation (CROSS protocol) | 2016-01-19 |  | No | Neither
14/LO/1378 | 124638 | The MPN Experimental Assessment of Symptoms by Utilizing Repetitive Evaluation (MEASURES) Trial: Serial Assessment of Symptomatic Response to Non Experimental Medical Therapies and/or Phlebotomy in Patients with Myeloproliferative Neoplasms | 2016-01-04 |  | No | Neither
14/NW/0036 | 139963 | ESPAC-5F: European Study Group for Pancreatic Cancer - Trial 5F Four arm, prospective, multicentre, randomised feasbility trial of immediate surgery compared with neoadjuvant chemotherapies and neoadjuvant chemoradiotherapy | 2016-01-04 |  | No | Neither
14/SC/1214 | 151677 | Effects of Regional Ischaemia and Blue Light on Nitric Oxide and Sulphide signalling (ERNIE) | 2016-03-22 |  | N/A
14/SC/1223 | 135378 | CALIBER | 2016-03-04 |  | N/A
14/SC/1329 | 157664 | STRIVE: A multicentre randomiSed controlled Trial of IntraVEnous immunoglobulin (IVIg) versus standard therapy for the treatment of transverse myelitis in adults and children | 2015-12-30 |  | No | Sponsor
14/SC/1366 | 135118 | A phase III clinical trial evaluation TheraSphere® in patients with metastatic colorectal carcinoma of the liver who have failed first line chemotherapy | 2016-01-04 |  | No | Neither
14/WM/1260 | 163072 | A phase Ib study to assess the safety and tolerability of oral Ruxolitinib in combination with 5-azacitidine in patients with advanced phase myeloproliferative neoplasms (MPN), including myelodysplastic syndromes (MDS) or acute myeloid leukaemia (AML) ari | 2016-01-18 |  | No | Neither
15/EE/0308 | 167511 | A three-arm, Randomised Controlled Trial of the effectiveness and cost-effectiveness of adjunctive medication management and contingency management to enhance adherence to medications for relapse prevention in alcohol dependence | 2016-01-18 |  | N/A
15/EE/0353 | 187464 | PCYC-1137 - Ibrutinib in Metastatic Pancreatic Adenocarcinoma | 2016-03-02 |  | N/A
15/EM/0344 | 183906 | A Randomized, Double-blind, Placebo-controlled Study of Safety and Efficacy of Amatuximab in Combination with Pemetrexed and Cisplatin in Subjects with Unresectable Malignant Pleural Mesothelioma | 2016-01-13 |  | No | Neither
15/LO/0304 | 162246 | Bubble: Phase 1B study of buparlisib with with bortezomib in defined genetic subgroups of patients with relapsed or refractory mutliple myeloma | 2016-01-04 |  | No | Neither
15/LO/0472 | 167100 | Comparison of the efficacy and safety of Thealoz-Duo® (T2762) versus Optive® in the treatment of moderate to severe Dry Eye Syndrome | 2016-01-08 |  | No | Sponsor
15/LO/0699 | 173824 | CHIL 4260 (VX14-661-108 - Cystic Fibrosis) | 2016-03-17 |  | N/A
15/LO/1015 | 182526 | Open-label Phase-4 study to examine the change of vision-related quality of life in subjects with diabetic macular edema (DME) during treatment with intravitreal injections of 2 mg aflibercept according to EU label for the first year of treatment | 2016-01-08 | 2016-02-17 | Yes
15/LO/1261 | 163080 | GAST 4460 (Ulcerative Colitis) | 2016-03-15 |  | N/A
15/LO/1353 | 186162 | A Phase 1 study to assess the safety and immunogenicity of a protein particle malaria vaccine candidate, R21, administered with AS01B in healthy UK volunteers | 2016-01-21 | 2016-02-15 | Yes
15/LO/1500 | 187068 | Drug-drug interaction study with nintedanib and pirfenidone | 2016-02-16 |  | N/A
15/LO/1670 | 188788 | Randomized, Placebo-Controlled, Double-Blind Phase 2 Study of Patritumab (U3 1287) in Combination with Cetuximab plus Platinum-Based Therapy in First Line Setting in Subjects with Recurrent or Metastatic Squamous Cell Carcinoma of the Head and Neck | 2016-01-04 |  | No | Neither
15/LO/1678 | 189439 | OPuS-4: An Open-Label Study to Evaluate the Long-Term Safety of Avoralstat in Subjects with Hereditary Angioedema | 2016-01-05 |  | No | Sponsor
15/LO/1788 | 184147 | Nevisense Evaluation in Southampton | 2016-01-22 |  | N/A
15/LO/1807 | 187302 | Checkmate 331 | 2016-03-04 |  | N/A
15/NE/0144 | 179243 | GAST 4684 | 2016-03-15 |  | N/A
15/NI/0145 | 158005 | Polatuzumab Vedotin in DLBCL | 2016-03-03 |  | N/A
15/SC/0219 | 170737 | An unblinded study of the feasibility of plasmapheresis or intravenous immunoglobulin, combined with corticosteroids, in patients with acute psychosis associated with anti-neuronal membrane auto-antibodies. | 2016-01-08 |  | No | Neither
15/SC/0306 | 176881 | A Phase 3, Randomized, Double-Blind, Placebo-Controlled Study of Ramucirumab plus Docetaxel versus Placebo plus Docetaxel in Patients with Locally Advanced or Unresectable or Metastatic Transitional Cell Carcinoma of the Urothelium who Progressed followin | 2016-01-25 |  | N/A
15/SC/0316 | 164933 | A multi-centre, randomised, double blind, placebo-controlled trial evaluating the effects of early administration of fibrinogen concentrate in adults with major traumatic haemorrhage | 2016-01-18 |  | N/A
15/SC/0397 | 183591 | An evaluation of the tolerance and acceptability of Neocate Junior an amino acid based feed for children | 2016-01-29 |  | N/A
15/SC/0403 | 180707 | Endostim for GORD in Asthma | 2016-03-10 |  | N/A
15/SC/0429 | 142341 | Prospective study of understudied drugs in children | 2016-03-02 | 2016-03-21 | Yes
15/SC/0475 | 174852 | An open label, randomized phase 3 trial of Nivolumab, or Nivolumab plus Ipilimumab, versus platinum doublet chemotherapy in subjects with chemotherapy-naive Stage IV or recurrent non-small cell lung cancer (NSCLC) (Checkmate 227) | 2016-01-18 |  | N/A
15/SC/0477 | 178062 | Hyperspectral Imaging Cancer Detection - HELICoiD B | 2016-01-14 | 2016-03-07 | Yes
15/SS/0186 | 190856 | A Phase II, Randomized, Open-Label Clinical Trial to Study the Efficacy and Safety of the Combination Regimen of Grazoprevir/Elbasvir (GZR/EBR) and Sofosbuvir (SOF) with and without Ribavirin (R) in Cirrhotic Subjects with Chronic HCV GT3 Infection | 2016-01-25 |  | N/A
15/WA/0384 | 188995 | Boston Scientific COMET Wire Validation Study | 2016-03-03 | 2016-03-22 | Yes
15/WM/0211 | 167913 | An Open-label, phase 1b Study of ACP-196 in Subjects with Multiple Myeloma | 2016-01-04 | 2016-03-09 | Yes
15/WM/0261 | 183481 | ALIFE 2 | 2016-03-09 |  | N/A
15/WS/0115 | 152112 | A Phase III, open-label, multicentre, randomised trial to establish safety and efficacy of an EGF cancer vaccine in inoperable, stage IV biomarker positive, wild type EGF-R NSCLC patients elgible to received standard treatment and supportive care | 2016-01-18 |  | N/A
15/WS/0135 | 183471 | A Phase 1b Dose Escalation and Dose Expansion Study of ONO/GS-4059 in Combination with other Targeted Anti-cancer Therapies in Subjects with B-cell Malignancies | 2016-03-02 |  | N/A
16/LO/0041 | 193238 | Trace Element Malnutrition in Paediatric Renal Disease | 2016-03-17 |  | N/A