## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay | Comments | Reasons for delay correspond to:
122493 | 16/SC/0601 | 209260 | Long Term Safety of Filgotinib in Active Ulcerative Colitis | Yes | 2017-10-25 | 56 | 28 | 84 | 2016-09-29 | 2017-08-02 | 2016-12-21 | 2017-09-27 | 2017-09-27 | Please Select... | 2017-09-27 | F - No patients seen H - Contracting delays | H: Contracting delays - Signed contract not received from the Sponsor until 27 Sep 2017. F: No eligible patients seen during the reported period. Patients sought but no eligible patients identified - a small patient population due to tight inclusion/exclusion criteria meant that few patients presented with the condition. | Sponsor
122494 | 17/LO/0683 | 226533 | VXECD101 | Yes | 2017-10-04 | 1 | 42 | 43 | 2017-03-03 | 2017-08-22 | 2016-12-22 | 2017-08-22 | 2017-08-23 | Please Select... | 2017-08-23 |  | Targets met | Please Select...
122495 | 17/EE/0115 | 218578 | Study to Evaluate Safety, Pharmacokinetics and Pharmacodynamics of FDL169 in Cystic Fibrosis | Yes | 2018-01-11 | 20 | 121 | 141 | 2016-12-13 | 2017-08-23 | 2017-07-11 | 2017-09-07 | 2017-09-12 | Please Select... | 2017-09-12 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 1 in 2500 fitting the EURORDIS definition. | Neither
122496 | 17/NE/0115 | 218417 | MA39189 | Yes | 2017-11-07 | 1 | 54 | 55 | 2017-07-27 | 2017-09-13 | 2017-05-26 | 2017-09-13 | 2017-09-14 | Please Select... | 2017-09-14 |  | Targets met | Please Select...
122497 | 17/LO/0182 | 213821 | FORTIFY Clinical trail | No |  | 1 |  |  | 2017-05-16 | 2017-09-19 | 2017-03-30 | 2017-09-19 | 2017-09-20 | Please Select... | 2017-09-22 | F - No patients seen | F: No eligible patients seen during the reported period - Patients sought but no eligible patients identified - a small patient population due to tight inclusion/exclusion criteria meant that few patients presented with the condition | Neither
122498 | 17/EM/0246 | 228635 | ZEPHYR | No |  | 7 |  |  | 2017-07-17 | 2017-09-19 | 2017-08-22 | 2017-09-20 | 2017-09-26 | Please Select... | 2017-09-26 | C - Closed by sponsor | C: Study closed by sponsor - Strategic/financial reasons within sponsor Company - closed 23/10/2017 | Sponsor
122499 | 17/SC/0271 | 226061 | RESULT: Reliable, Emergent Solution Using Liprotamase Treatment | Yes | 2017-10-25 | 15 | 13 | 28 | 2017-09-12 | 2017-09-27 | 2017-09-20 | 2017-10-02 | 2017-10-12 | Please Select... | 2017-10-12 |  | Targets met | Please Select...
122500 | 17/LO/0380 | 218003 | BN29553 (CREAD-2) - Crenezumab in patients with Prodromal to Mild AD | Yes | 2017-10-05 | 6 | 65 | 71 | 2017-01-16 | 2017-07-26 | 2017-05-18 | 2017-08-01 | 2017-08-01 | Please Select... | 2017-08-01 | F - No patients seen | F: No eligible patients seen between date site selected plus 70 days 114 patients screened. Patients sought but no eligible patients identified - a small patient population due to tight inclusion/exclusion criteria meant that few patients presented with the condition. 1st participant recruited 05/10/2017. | Neither
122501 | 16/EM/0459 | 213319 | Adults with RSV | Yes | 2017-12-08 | 5 | 107 | 112 | 2016-09-29 | 2017-08-18 | 2017-03-29 | 2017-08-23 | 2017-08-23 | Please Select... | 2017-08-23 | B - Suspended by sponsor | B: Study temporarily suspended by sponsor. | Sponsor
122502 | 17/SC/0345 | 225047 | A Single-dose Pharmacokinetics Study of MK-7655A in Pediatric Subjects | No |  | 84 |  |  | 2017-04-21 | 2017-10-19 | 2017-10-05 | 2018-01-11 | 2018-01-11 | Please Select... | 2018-01-11 | B - Suspended by sponsor D - Sponsor Delays | D: Delay by sponsor - Delay in provision of pharmacy manual - Final pharmacy manual not received until 03/01/2018. Delay in delivering IMP to site, First delivery received 16/02/2018 but experienced a temperature excursion in transit so still awaiting new delivery. B: Study suspended by sponsor. | Sponsor
122503 | 17/LO/0041 | 219676 | CardioMEMS HF System OUS Post Approval Study | Yes | 2017-08-16 | 0 | 15 | 15 | 2017-04-26 | 2017-08-01 | 2017-03-06 | 2017-06-06 | 2017-08-01 | Please Select... | 2017-08-01 |  | Targets met | Please Select...
122504 | 17/NW/0175 | 222859 | PRTX-100 in ITP | Yes | 2017-10-09 | 13 | 68 | 81 | 2017-03-01 | 2017-07-20 | 2017-05-19 | 2017-06-19 | 2017-08-02 | Please Select... | 2017-08-02 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 5.6 per 100,000 fitting the EURORDIS definition. | Neither
122505 | 17/EE/0221 | 223856 | CC-90001-IPF-001 - safety and efficacy of CC90001 in patients with IPF | Yes | 2018-05-29 | 1 | 201 | 202 | 2017-03-17 | 2017-11-08 | 2017-09-14 | 2017-11-09 | 2017-11-09 | Please Select... | 2018-02-06 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 12.3 per 100,000 fitting the EURORDIS definition. | Neither
122506 | 17/LO/0794 | 223700 | RHCF | Yes | 2018-01-30 | 3 | 166 | 169 | 2017-06-05 | 2017-08-14 | 2017-07-28 | 2017-06-15 | 2017-08-17 | Please Select... | 2017-08-17 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 23.1 per 100,000 fitting the EURORDIS definition. | Neither
122507 | 17/NE/0124 | 216591 | TEMPO Study | Yes | 2018-03-19 | 4 | 129 | 133 | 2017-05-23 | 2017-11-06 | 2017-07-10 | 2017-11-10 | 2017-11-10 | Please Select... | 2018-01-04 | D - Sponsor Delays F - No patients seen | D: Delays caused by sponsor: Delayed confirmation from sponsor of study open to recruitment at site Green light not given by Sponsor until 04/01/2018. F: No eligible patients seen during the reported period. Patients sought but no eligible patients identified - a small patient population due to tight inclusion/exclusion criteria. Only expect to recruit 3 patients in 1 year. | Sponsor
122508 | 16/SC/0631 | 209258 | A Long-Term Extension Study to Evaluate the Safety of Filgotinib in Subjects with Crohn's Disease | No |  | 3 |  |  | 2017-09-29 | 2017-10-02 | 2017-01-17 | 2017-10-05 | 2017-10-05 | Please Select... | 2017-10-05 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 34 per 100,000 fitting the EURORDIS definition. | Neither
122510 | 17/EE/0204 | 207238 | BCX7353 as a treatment for acute HAE attacks | Yes | 2018-01-09 | 18 | 42 | 60 | 2017-04-26 | 2017-11-10 | 2017-07-19 | 2017-11-29 | 2017-11-28 | Please Select... | 2017-11-29 |  | Met Target | Please Select...
122511 | 17/SC/0462 | 228889 | VAC18194 (AD26.RSV.preF) | Yes | 2017-12-07 | 48 | 8 | 56 | 2017-08-03 | 2017-10-12 | 2017-10-04 | 2017-11-29 | 2017-11-29 | Please Select... | 2017-11-29 |  | Met Target | Please Select...
122512 | 17/YH/0295 | 230804 | CR6086-2-02 | No |  | 5 |  |  | 2017-09-20 | 2017-12-01 | 2017-10-23 | 2017-12-06 | 2017-12-06 | Please Select... | 2017-12-27 | F - No patients seen | F: No eligible patients seen during the reported period - Patients sought but no eligible patients identified: a small patient population due to tight inclusion/exclusion criteria. Expected recruitment of 2 patients in 1 year. | Neither
122513 | 17/WM/0308 | 226910 | ALPINE 2: AZLI for children with CF and PA lung infection | Yes | 2018-06-21 | 6 | 182 | 188 | 2017-04-06 | 2017-12-15 | 2017-10-09 | 2017-12-21 | 2017-12-21 | Please Select... | 2018-01-02 | F - No patients seen | F:No eligible patients identified: a small patient population due to tight inclusion/exclusion criteria. Expected recruitment of 2 patients in 3 years. | Neither
122515 | 17/EM/0301 | 209448 | The SANDWICH Trial | Yes | 2018-02-06 | 22 | 53 | 75 | 2017-06-30 | 2017-11-23 | 2017-09-29 | 2017-12-15 | 2017-12-15 | Please Select... | 2017-12-18 | D - Sponsor Delays | D: Delays caused by sponsor: Sponsor has delayed opening randomisation until February 2018. | Sponsor
122517 | 16/SC/0271 | 187103 | plasmaMATCH | Yes | 2018-02-19 | 7 | 26 | 33 | 2016-11-09 | 2018-01-17 | 2016-09-21 | 2017-12-19 | 2018-01-24 | Please Select... | 2018-02-19 |  | Targets met | Please Select...
122519 | 16/YH/0225 | 198518 | I-BiT Plus version 1.0 | Yes | 2018-03-28 | 1 | 84 | 85 | 2017-07-14 | 2018-01-02 | 2016-08-10 | 2017-01-04 | 2018-01-03 | Please Select... | 2018-01-04 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 32.1 per 100,000 fitting the EURORDIS definition. | Neither
122520 | 17/SC/0008 | 215740 | Module 3: Development of an effective and comfortable penile compression device | No |  | 28 |  |  | 2017-08-14 | 2018-02-20 | 2017-07-26 | 2018-02-07 | 2018-03-20 | Please Select... | 2018-03-20 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 1.2 per 100,000 fitting the EURORDIS definition. | Neither
122521 | 16/NW/0629 | 211995 | CF START | Yes | 2018-04-11 | 74 | 99 | 173 | 2017-08-07 | 2017-10-20 | 2016-09-22 | 2018-01-02 | 2018-01-02 | Please Select... | 2018-01-02 | H - Contracting delays I - Rare diseases | H: Contracting delays - Signed contract not received from the Sponsor until 29/12/2017. I: Rare disease 40 cases per 100,000 which fits the EURORDIS definition. | Sponsor
122523 | 17/LO/0525 | 221541 | Aerie PG324 Ophthalmic Solution | No |  | 7 |  |  | 2017-12-13 | 2018-01-09 | 2017-06-30 | 2017-11-21 | 2018-01-16 | Please Select... | 2018-01-25 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 11.5 per 100,000 fitting the EURORDIS definition. | Neither
122524 | 16/WS/0093 | 200488 | FAK-PD1 v1 | Yes | 2018-01-18 | 3 | 87 | 90 | 2017-04-27 | 2017-10-20 | 2017-04-25 | 2017-10-23 | 2017-10-23 | Please Select... | 2017-12-12 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 0.88 per 100,000 fitting the EURORDIS definition. | Neither
122525 | 17/YH/0120 | 208838 | DISC - Dupuytren's Interventions Surgery vs Collagenase | Yes | 2017-11-21 | 61 | 55 | 116 | 2017-05-02 | 2017-07-28 | 2017-05-25 | 2017-09-27 | 2017-09-27 | Please Select... | 2017-09-27 | H - Contracting delays I - Rare diseases | H: Contracting delays - Signed contract not received from the Sponsor until 26 Sep 2017 I: Rare disease 34.4 cases per 100,000 fitting the EURORDIS Definition. | Sponsor
122526 | 16/SC/0462 | 208830 | DRAFFT 2 - Distal Radius Acute Fracture Fixation Trial 2 | Yes | 2017-09-22 | 21 | 45 | 66 | 2016-10-10 | 2017-07-18 | 2016-12-11 | 2017-08-08 | 2017-08-08 | Please Select... | 2017-08-18 |  | Met Target | Please Select...
122531 | 17/WS/0008 | 218692 | STARDUST - CNTO1275CRD3005 | Yes | 2018-05-21 | 0 | 88 | 88 | 2017-04-06 | 2018-02-22 | 2017-03-24 | 2018-02-22 | 2018-02-22 | Please Select... | 2018-02-22 |  | I: Rare diseases study: Condition being studied has an incidence of 10.7 per 100,000 fitting the EURORDIS definition. | Please Select...
122532 | 17/EE/0101 | 222212 | Altura Post-Market Registry Study: Altitude Registry | No |  | 316 |  |  | 2017-06-14 | 2017-09-06 | 2017-05-04 | 2018-05-14 | 2018-07-19 | Please Select... | 2018-07-19 | B - Suspended by sponsor | B: Study suspended by sponsor: Study set-up suspended at all sites as Sponsor company are going through financial restructure. | Sponsor
122534 | 17/WM/0169 | 219535 | RECORD | No |  | 114 |  |  | 2017-06-06 | 2017-11-28 | 2017-06-06 | 2018-03-19 | 2018-03-22 | Please Select... | 2018-03-22 | C - Closed by sponsor | C: Study closed by sponsor. The project has been terminated because the trials funding has been exhausted. | Sponsor
122535 | 17/SC/0164 | 210735 | Early cryoprecipitate in major trauma haemorrhage: CRYOSTAT-2 | Yes | 2017-10-08 | 7 | 5 | 12 | 2017-03-23 | 2017-09-26 | 2017-05-26 | 2017-10-03 | 2017-10-03 | Please Select... | 2017-10-03 |  | Met Target | Please Select...
122536 | 17/LO/0371 | 212841 | ODAK Phase 3 (043/SI) | Yes | 2018-05-18 | 19 | 235 | 254 | 2017-06-13 | 2017-09-06 | 2017-06-19 | 2017-09-18 | 2017-09-25 | Please Select... | 2017-09-25 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 14.9 per 100,000 fitting the EURORDIS definition. | Neither
122537 | 17/LO/1060 | 187783 | SUBsensory Sacral Neuromodulation for InContinence - SUBSoNIC | Yes | 2018-05-15 | 29 | 168 | 197 | 2017-05-11 | 2017-10-30 | 2017-09-29 | 2017-10-30 | 2017-11-28 | Please Select... | 2017-11-28 | F - No patients seen | F: No eligible patients seen. Patients sought but no eligible patients identified - a small patient population due to tight inclusion/exclusion criteria - expected to recruit 5 patients in 3 years. | Neither
122538 | 17/SC/0256 | 164524 | Investigation into the Immuno-modulatory mechanisms of exercise in moderate atopic asthma - a pilot study | Yes | 2017-10-31 | 2 | 26 | 28 | 2017-03-02 | 2017-10-03 | 2017-07-31 | 2017-10-05 | 2017-10-05 | Please Select... | 2017-10-05 |  | Met Target | Please Select...
122539 | 17/NW/0439 | 227566 | CA209-914 Nivolumab in Patients with Renal Cell Carcinoma | No |  | 137 |  |  | 2017-04-18 | 2017-10-26 | 2017-10-13 | 2017-12-11 | 2018-03-12 | Please Select... | 2018-05-03 | A - Permissions delayed/denied D - Sponsor Delays | A: Relevant permissions delayed and not granted in time - SSA Exemption for the Nuffield Hospital was not received until 09/03/2018 D: Delays caused by sponsor: Delayed confirmation from sponsor of study open to recruitment at site - delays in receiving Green Light Green light received 03/05/2018 | Sponsor
122540 | 17/SC/0454 | 230182 | CITADEL-204 | No |  | 181 |  |  | 2017-07-04 | 2017-10-04 | 2017-10-19 | 2018-03-14 | 2018-04-03 | Please Select... | 2018-05-04 | D - Sponsor Delays F - No patients seen | H: Contracting delays - Sponsor company did not return the contract until 16/03/2018. D: Delays caused by sponsor: Delayed confirmation from sponsor of study open to recruitment at site - delays in receiving Green Light - Green light received 04/05/2018. | Sponsor
122541 | 17/YH/0150 | 223266 | BEAR Men B | Yes | 2017-10-06 | 28 | 37 | 65 | 2016-09-07 | 2017-08-02 | 2017-07-05 | 2017-08-02 | 2017-08-30 | Please Select... | 2017-08-30 |  | Met Target | Please Select...
122542 | 17/NS/0018 | 223787 | The Future Study | Yes | 2018-01-10 | 3 | 37 | 40 | 2017-09-07 | 2017-12-01 | 2017-10-01 | 2017-10-01 | 2017-12-04 | Please Select... | 2017-12-04 |  | Met Target | Please Select...
122544 | 17/SC/0340 | 225542 | MEDI0680 with Durvalumab vs Nivolumab Alone | Yes | 2018-05-23 | 189 | 48 | 237 | 2016-07-15 | 2017-09-28 | 2017-11-01 | 2018-02-05 | 2018-04-05 | Please Select... | 2018-05-18 | D - Sponsor Delays H - Contracting delays | H: Contracting delays - Sponsor company did not return the contract until 09/02/2017. D: Delays caused by sponsor: Delay in provision of pharmacy manual - not received until 28/03/2018: Delayed confirmation from sponsor of study open to recruitment at site - delays in receiving Green Light - Green light received on 18/05/2018. First patient recruited 5 days after green light given. | Sponsor
122545 | 17/SW/0257 | 229898 | Treatment of Neck and Upper Limb Pain using BurstDRTM Stimulation (NU-BURST) | No |  | 26 |  |  | 2017-10-19 | 2018-02-22 | 2018-01-19 | 2018-02-27 | 2018-03-20 | Please Select... | 2018-03-21 | F - No patients seen | F: No eligible patients seen during the reported period: Patients sought but no eligible patients identified. Patients were screened but none were eligible, a small patient population due to tight inclusion/exclusion criteria. | Neither
122546 | 17/SW/0207 | 231037 | The FORECAST Trial | Yes | 2017-12-05 | 30 | 25 | 55 | 2017-06-20 | 2017-10-11 | 2017-10-03 | 2017-12-04 | 2017-11-10 | Please Select... | 2017-12-04 |  | Met Target | Please Select...
122548 | 17/EM/0371 | 229496 | 0393/0028 SMART CRT | Yes | 2018-05-02 | 107 | 111 | 218 | 2017-06-23 | 2017-09-26 | 2017-11-21 | 2018-01-11 | 2018-01-11 | Please Select... | 2018-01-11 | F - No patients seen H - Contracting delays | H: Contracting delays - Sponsor company did not return the contract until 11/01/2018. F: Few eligible patients seen during the reported period - (13 patients screened and none eligible) - a small patient population due to tight inclusion/exclusion criteria - expected to recruit 3 patients in 2 years. | Sponsor
122549 | 17/SC/0268 | 222138 | Uterine Fibroid Embolization (UFE) for Symptomatic Fibroids: Comparison of Gel-Bead to Commonly Used Embolic Agents. | Yes | 2017-07-24 | 3 | 0 | 3 | 2017-03-06 | 2017-07-21 | 2017-07-05 | 2017-07-24 | 2017-07-24 | Please Select... | 2017-07-24 |  | Met Target | Please Select...
122550 | 17/LO/0365 | 216598 | Improving Fundamental Care in Hospitals | Yes | 2017-09-06 | 60 | 1 | 61 | 2017-06-08 | 2017-07-07 | 2017-04-28 | 2017-09-05 | 2017-09-05 | Please Select... | 2017-09-05 |  | Met Target | Please Select...
122551 | 17/SC/0317 | 223132 | RiVa | No |  | 141 |  |  | 2016-12-21 | 2017-09-06 | 2017-09-06 | 2018-01-25 | 2018-01-25 | Please Select... | 2018-02-22 | H - Contracting delays I - Rare diseases | H: Contracting delays: Signed contract not received from the Sponsor until 25/01/2018. I: Rare disease study: Condition being studied has an incidence of 5 per 100,000 fitting the EURORDIS definition. | Sponsor
122555 | 17/SC/0342 | 229497 | Investigating the Effects of a Structured Responsive Exercise Training Programme on Idiopathic Pulmonary Fibrosis - A Pilot Study (REHAB-IPF) | Yes | 2017-09-22 | 0 | 29 | 29 | 2017-06-08 | 2017-08-24 | 2017-08-02 | 2017-08-24 | 2017-08-24 | Please Select... | 2017-08-24 |  | Met Target | Please Select...
122556 | 17/WM/0425 | 232819 | A clinical trial involving research of the house dust mite SLIT-tablet | No |  | 1 |  |  | 2017-05-23 | 2018-03-07 | 2018-01-15 | 2018-03-06 | 2018-03-08 | Please Select... | 2018-03-08 | F - No patients seen | F: No eligible patients seen during the reported period: Patients sought but no eligible patients identified. Patients were screened but none were eligible, a small patient population due to tight inclusion/exclusion criteria. Study has failed to recruit nationally. | Neither
122560 | 17/SC/0368 | 229629 | Molecular point-of-care 'test and treat' for influenza (FluPOC) v1.0 | Yes | 2017-12-12 | 2 | 54 | 56 | 2017-06-14 | 2017-10-17 | 2017-09-07 | 2017-10-19 | 2017-10-19 | Please Select... | 2017-10-19 |  | Met Target | Please Select...
122562 | 17/SC/0638 | 236603 | BCX7353 long term safety study | Yes | 2018-02-27 | 14 | 21 | 35 | 2017-11-23 | 2018-01-23 | 2018-01-25 | 2018-01-10 | 2018-02-06 | Please Select... | 2018-02-06 |  | Met Target | Please Select...
122564 | 17/LO/2061 | 236799 | CAPOEIRA-I | Yes | 2018-02-08 | 8 | 7 | 15 | 2017-06-16 | 2018-01-24 | 2018-01-24 | 2018-02-01 | 2018-02-01 | Please Select... | 2018-02-01 |  | Met Target | Please Select...
122565 | 18/SC/0018 | 232917 | PULSe Ox | Yes | 2018-03-14 | 28 | 15 | 43 | 2017-08-31 | 2018-01-30 | 2018-01-31 | 2018-02-27 | 2018-02-27 | Please Select... | 2018-02-27 |  | Met Target | Please Select...
122566 | 18/SW/0002 | 233850 | CONSTANT | Yes | 2018-05-10 | 11 | 51 | 62 | 2017-08-30 | 2018-03-09 | 2018-02-20 | 2018-03-08 | 2018-03-20 | Please Select... | 2018-03-20 |  | Met Target | Please Select...
122568 | 17/SC/0641 | 238111 | BMN270-203 Gene Therapy Study in Patients with Antibodies Against AAV5 | Yes | 2018-04-03 | 109 | 7 | 116 | 2017-10-23 | 2017-12-08 | 2018-02-01 | 2018-03-22 | 2018-03-27 | Please Select... | 2018-03-28 | H - Contracting delays | H: Contracting delays - Signed contract not received from the Sponsor until 27/03/2017. First participant recruited 03/04/2017. | Sponsor
122571 | 17/EM/0166 | 222665 | AVAIL-T - Avelumab in relapsed/refractory T-cell Lymphoma | No |  | 54 |  |  | 2017-06-26 | 2018-02-16 | 2017-03-30 | 2018-03-23 | 2018-04-11 | Please Select... | 2018-05-08 | D - Sponsor Delays H - Contracting delays I - Rare diseases | H: Contracting delay: Sponsor did not return a signed contract until 26/04/2018. D: Sponsor Delay: Sponsor did not issue the green light until 11/05/2018. I: Rare diseases study: Condition being studied has an incidence of 0.75 per 100,000 fitting the EURORDIS definition. | Sponsor
124716 | 16/LO/1099 | 181655 | TIGER: A RANDOMIZED PHASE III TRIAL COMPARING CONVENTIONAL-DOSE CHEMOTHERAPY | Yes | 2018-05-04 | 252 | 11 | 263 | 2016-10-11 | 2017-08-14 | 2016-11-01 | 2018-02-16 | 2018-04-23 | Please Select... | 2018-04-25 | D - Sponsor Delays | D: Sponsor Delays: UHS have been ready since October 2017 but were awaiting the Sponsor, who was not ready to open, to indicate they were ready for UHS to confirm Capacity and Capability. Green light given on 25/04/2018. | Sponsor
124717 | 17/EE/0317 | 230053 | Study of AZD4573 in Relapsed or Refractory Haematological Malignancies | No |  | 254 |  |  | 2017-08-29 | 2017-08-30 | 2017-09-27 | 2018-01-24 | 2018-05-11 | Please Select... | 2018-07-02 | A - Permissions delayed/denied D - Sponsor Delays I - Rare diseases | A: Relevant Permissiond delayed and not granted in time: This is a phase 1 study and therefore had to be approved by the phase 1 safety committee in order to comply with the MHRA Phase 1 accreditation scheme. D: Sponsor delays: Sponsor would not accept the costings for the study and the final version that was agreed of the costing template was 5. I: Rare diseases study: Condition being studied has an incidence of 7.5 per 100,000 fitting the EURORDIS definition. | Sponsor
124718 | 17/LO/0984 | 218704 | A Phase I trial of AST-VAC2 vaccine in patients with NSCLC | Yes | 2018-05-17 | 221 | 16 | 237 | 2017-03-30 | 2017-09-22 | 2017-09-21 | 2018-04-26 | 2018-05-01 | Please Select... | 2018-05-11 | D - Sponsor Delays H - Contracting delays I - Rare diseases | H: Contracting delay: Sponsor did not return a signed contract until 26/04/2018. D: Sponsor Delay: Sponsor did not issue the green light until 11/05/2018. I: Rare diseases study: Condition being studied has an incidence of 43 per 100,000 fitting the EURORDIS definition. | Sponsor
124719 | 17/NE/0311 | 229481 | GO39733 | No |  | 208 |  |  | 2017-08-29 | 2017-10-26 | 2017-11-22 | 2018-04-19 | 2018-05-22 | Please Select... | 2018-05-31 | D - Sponsor Delays | D: Sponsor Delays: Sponsor was not planning on opening any UK sites until April 2018 but sent out the local pack well in advance. The sponsor also then amended the protocol and we had to wait for approval for this prior to confirming capacity and capability. | Sponsor
124720 | 17/SC/0121 | 209428 | PemBla | No |  | 204 |  |  | 2017-01-26 | 2017-11-01 | 2017-06-16 | 2018-05-15 | 2018-05-24 | Please Select... |  | D - Sponsor Delays H - Contracting delays | H: Contracting delays: Signed contract not received fromt he SPonsor until 22/05/2018. D: Sponsor delays: Green light from the sponsor is still awaited. | Sponsor
124721 | 17/SC/0387 | 208972 | MiNivAN trial | Yes | 2018-06-26 | 174 | 49 | 223 | 2017-07-18 | 2017-11-15 | 2017-11-10 | 2018-05-08 | 2018-05-08 | Please Select... | 2018-05-15 | D - Sponsor Delays | D: Sponsor Delays: Notified that the Sponsor was submitting a protocol amendment and therefore study would not open until this had been approved. Sponsor did not arrange the SIV until 15/05/2018. | Sponsor
124722 | 17/SC/0615 | 233555 | VIOLETTE | No |  | 168 |  |  | 2017-10-16 | 2017-12-07 | 2018-03-16 | 2018-04-09 | 2018-05-24 | Please Select... | 2018-07-05 | A - Permissions delayed/denied D - Sponsor Delays | A: Regulatory approvals not given in time: HRA approval recieved 05/01/2018. SSA exemption for the use of off site scanning not confirmed until 26/04/2018. D: Sponsor Delay: Delay in providing documents to pharmacy for review and set-up. Green light still awaited. | Sponsor
124723 | 17/EM/0378 | 134320 | Randomised controlled trial in adolescent scoliosis surgery: K2M rail versus USS2 | Yes | 2018-03-13 | 74 | 25 | 99 | 2012-07-21 | 2017-12-04 | 2017-12-04 | 2018-02-16 | 2018-02-16 | Please Select... | 2018-02-19 | D - Sponsor Delays | D: Sponsor Delays: Green light not given until 19/02/2018. H: Contracting delays: Signed contract not received from the Sponsor until 16/02/2018 | Sponsor
124724 | 17/LO/1918 | 229435 | NESIC Version 1.0 | No |  | 6 |  |  | 2017-11-16 | 2018-05-23 | 2018-01-29 | 2018-05-12 | 2018-05-29 | Please Select... | 2018-05-30 |  | Not yet past target. | Please Select...
124725 | 17/SC/0533 | 205320 | ARGO | No |  | 175 |  |  | 2017-10-03 | 2017-12-06 | 2018-01-31 | 2018-05-30 | 2018-05-30 | Please Select... | 2018-06-21 | D - Sponsor Delays | D: Sponsor delays: Confirmation by sponsor delayed. Not received until 30/05/2018. | Sponsor
124726 | 17/LO/2017 | 226844 | CROS hearing aid management | Yes | 2018-02-27 | 28 | 39 | 67 | 2017-11-10 | 2017-12-22 | 2017-12-13 | 2018-01-19 | 2018-01-19 | Please Select... | 2018-01-19 |  | Targets met | Please Select...
124727 | 16/SC/0551 | 214620 | XIRIUS | No |  | 33 |  |  | 2017-08-14 | 2017-12-28 | 2017-01-19 | 2017-12-19 | 2018-01-30 | Please Select... | 2018-01-31 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 33 per 100,000 fitting the EURORDIS definition. | Neither
124728 | 17/LO/1695 | 234684 | BMN 270-301: Gene Therapy Study in Severe Haemophilia A Patients | Yes | 2018-06-15 | 152 | 10 | 162 | 2017-11-28 | 2018-01-04 | 2017-11-24 | 2018-05-29 | 2018-06-05 | Please Select... | 2018-06-22 | D - Sponsor Delays | D: Sponsor delay. Site confirmed by sponsor 29/05/2018 and green light not given until 22/06/2018. | Sponsor
124729 | 17/EE/0429 | 234063 | Evaluation of Lumicitabine in young children hospitalized with RSV | No |  |  |  |  | 2017-09-25 | 2018-01-10 | 2018-01-09 |  |  | Please Select... |  | B - Suspended by sponsor | B: study suspended by sponsor at all sites 21/02/2018, prior to confirmation of capacity and capability being given. | Sponsor
124730 | 17/YH/0369 | 232340 | BGB-3111-304 | No |  | 98 |  |  | 2017-10-16 | 2018-01-17 | 2018-01-03 | 2018-04-18 | 2018-04-25 | Please Select... | 2018-05-31 | D - Sponsor Delays H - Contracting delays I - Rare diseases | H:contracting delays: signed contract not received backfrom sponsor until 24/04/2018. D: Sponsor delays: SIV not arranged until 29/05/2018 which was the Sponsor plan from the beginning. Green light given 31/05/2018. I: Rare diseases study: Condition being studied has an incidence of 4 to 7 per 100,000 fitting the EURORDIS definition. | Sponsor
124731 | 17/LO/0657 | 217991 | ITACS Trial | No |  | 154 |  |  | 2018-01-10 | 2018-01-23 | 2017-06-06 | 2018-05-01 | 2018-06-26 | Please Select... | 2018-06-26 | D - Sponsor Delays H - Contracting delays | H: Contracting delay: Signed contract not received from the Sponsor until 01/05/2018. D: Sponsor delay. SIV date not set until 21/06/2018 and green light not given until 26/06/2018. | Sponsor
124732 | 17/EE/0448 | 226368 | CHILLY-AF | No |  | 104 |  |  | 2017-11-02 | 2018-01-30 | 2017-12-19 | 2018-05-14 | 2018-05-14 | Please Select... | 2018-05-14 | D - Sponsor Delays | D: Sponsor delay. Date site confirmed by sponsor 14/05/2018. | Sponsor
124733 | 16/YH/0206 | 185365 | BONES: The British Osteonecrosis Study | Yes | 2018-02-09 | 0 | 8 | 8 | 2017-04-03 | 2018-02-01 | 2017-02-06 | 2018-02-01 | 2018-02-01 | Please Select... | 2018-02-01 |  | Targets met | Please Select...
124734 | 17/LO/0736 | 225746 | Evaluate the Efficacy and Safety of Intravenously Administered BMS-986168 | Yes | 2018-05-18 | 77 | 24 | 101 | 2017-08-04 | 2018-02-06 | 2017-07-21 | 2018-04-19 | 2018-04-24 | Please Select... | 2018-04-25 | D - Sponsor Delays I - Rare diseases | D: Sponsor Delays: SIV not arranged until 25/04/2018. H: Contracting delays: Signed contract not received until 24/04/2018 I: Rare diseases study: Condition being studied has an incidence of 5 per 100,000 fitting the EURORDIS definition. | Sponsor
124735 | 17/LO/1149 | 220763 | Phase 3 study of Maribavir vs Valganciclovir in CMV infection in HSCT | No |  | 118 |  |  | 2017-04-18 | 2018-02-08 | 2017-09-12 | 2018-05-07 | 2018-06-06 | Please Select... | 2018-06-28 | D - Sponsor Delays | D: Sponsor delays: Documentation for pharmacy not received until 24/05/2018. SIV not arranged until 15/06/2018 and green light given 28/06/2018 | Sponsor
124736 | 17/SW/0127 | 225959 | Flight-A multicentre randomised trial of First Line treatment pathways for newly diagnosed Immune Thrombocytopenia: Standard steroid treatment versus combined steroid and mycophenolate | No |  | 112 |  |  | 2017-12-07 | 2018-02-14 | 2017-07-03 | 2018-05-09 | 2018-06-06 | Please Select... | 2018-07-06 | H - Contracting delays J - Other | H: Contracting delay: Signed contract not received until 17/05/2018. J: Other: Excess Traetment costs denied by the CRN and therefore funds had to be found in order to continue with the study. | Sponsor
124737 | 17/LO/1461 | 230430 | Study to understand if a vaccine can prevent flare ups of your COPD | Yes | 2018-04-04 | 6 | 29 | 35 | 2017-07-13 | 2018-02-28 | 2017-10-10 | 2018-02-28 | 2018-03-06 | Please Select... | 2018-03-07 |  | Targets met | Please Select...
124738 | 17/NW/0529 | 226070 | PPAC2: Packing of Perianal Abscess Cavities 2 | No |  | 124 |  |  | 2017-08-17 | 2018-03-01 | 2017-12-05 | 2018-05-03 | 2018-07-03 | Please Select... | 2018-07-03 | E - Staff availability issues H - Contracting delays | E: Staff availability issues at site: Delay in receiving the CV from the PI. H: Contracting delay: Signed copy of the contract not received until 21/05/2018. | Both
124739 | 18/LO/0535 | 239149 | Genomics and Proteomics in Coronary Artery Disease | Yes | 2018-05-22 | 39 | 28 | 67 | 2018-02-15 | 2018-03-16 | 2018-03-29 | 2018-04-24 | 2018-04-24 | Please Select... | 2018-04-24 |  | Targets met | Please Select...
124740 | 17/EM/0468 | 234972 | A3921104 - Tofacitinib for treatment of Juvenile Idiopathic Arthritis | No |  | 21 |  |  | 2017-07-12 | 2018-03-27 | 2018-03-27 | 2018-04-17 | 2018-04-17 | Please Select... | 2018-04-17 | I - Rare diseases | I: Rare diseases study: Condition being studied has an incidence of 13.9 per 100,000 fitting the EURORDIS definition. | Neither
124741 | 17/NE/0351 | 235420 | Evaluation of the MCM5 ELISA in the diagnosis of Prostate Cancer | Yes | 2018-06-18 | 70 | 13 | 83 | 2018-01-18 | 2018-03-27 | 2018-01-02 | 2018-05-31 | 2018-06-05 | Please Select... | 2018-06-11 | D - Sponsor Delays H - Contracting delays | D: Sponsor Delays: Green light not given until 11/06/2018. H: Contracting delays: signed contract not received until 04/06/2018 | Sponsor
124742 | 17/LO/1334 | 217338 | TOXYC: Targeted OXYgen therapy in Critical illness | Yes | 2018-05-11 | 3 | 32 | 35 | 2017-03-23 | 2018-04-06 | 2017-11-13 | 2018-04-06 | 2018-04-09 | Please Select... | 2018-04-09 |  | Targets met | Please Select...
124743 | 18/NW/0018 | 236551 | Renastep | Yes | 2018-06-07 | 53 | 6 | 59 | 2017-07-25 | 2018-04-09 | 2018-04-06 | 2018-05-24 | 2018-06-01 | Please Select... | 2017-07-25 |  | Targets met | Please Select...
124744 | 18/SC/0055 | 239091 | Be on the TEAM: Teenagers Against Meningitis | Yes | 2018-05-15 | 2 | 32 | 34 | 2017-11-07 | 2018-04-11 | 2018-03-05 | 2018-04-04 | 2018-04-13 | Please Select... | 2018-04-13 |  | Targets met | Please Select...
124745 | 18/LO/0364 | 237978 | Nalu Medical NAL-02-2016-FS SCS Feasibility trial | Yes | 2018-06-18 | 23 | 32 | 55 | 2018-01-18 | 2018-04-24 | 2018-04-23 | 2018-05-14 | 2018-05-17 | Please Select... | 2018-05-17 |  | Targets Met | Please Select...
124746 | 17/NE/0339 | 214254 | The CLEAR Trial | No |  | 69 |  |  | 2017-10-17 | 2018-04-25 | 2018-02-06 | 2017-07-03 | 2018-07-03 | Please Select... | 2018-07-03 | H - Contracting delays | H: Contracting delays: Signed contract not received until 03/07/2018. | Sponsor
124747 | 17/SC/0582 | 234404 | Long-term Safety Study of AR101 | Yes | 2018-06-13 | 22 | 13 | 35 | 2017-10-25 | 2018-05-09 | 2018-01-18 | 2018-05-31 | 2018-05-31 | Please Select... | 2018-06-01 |  | Targets Met | Please Select...
124748 | 10/H0803/121 | 53663 | Genetic Linkage Evaluation in ICCs v1 | No |  | 26 |  |  | 2017-12-18 | 2018-06-01 | 2016-08-02 | 2018-06-27 | 2018-06-27 | Please Select... | 2018-06-28 |  | Not yet past target | Please Select...
124749 | 14/EE/1293 | 164389 | C-STICH | Yes | 2018-06-19 | 0 | 18 | 18 | 2018-03-08 | 2018-06-01 | 2016-08-10 | 2018-05-11 | 2018-06-01 | Please Select... | 2018-06-01 |  | 1st participant recruiteed 18 days after date site selected. | Please Select...
124750 | 16/EE/0380 | 211295 | Day and night closed-loop in young people with type 1 diabetes (DAN05) | No |  | 1 |  |  | 2018-02-27 | 2018-06-14 | 2017-02-22 | 2018-05-15 | 2018-06-15 | Please Select... | 2018-06-18 |  | Not yet past target | Please Select...
124751 | 17/LO/1015 | 223251 | AIR - Ankle Injury Rehabilitation | Yes | 2018-05-08 | 65 | 27 | 92 | 2017-09-19 | 2018-02-05 | 2017-07-04 | 2018-04-05 | 2018-04-11 | Please Select... | 2018-04-11 | H - Contracting delays | H: Contracting Delays: Sponsor insisted that UHS sign before they did. Signed contract sent to them on 15/02/2018 but fully signed contract not received back until 11/04/2018. | Sponsor