## Sheet1
Id | Research Ethics Committee Reference Number | Integrated Research Application System Number | Name of Trial | First Participant Recruited? | Date of First Participant Recruited | Duration between Date Site Selected and Date Site Confirmed | Duration between Date Site Confirmed and First Participant Recruited | Duration between Date Site Selected and First Participant Recruited | Date Site Invited | Date Site Selected | HRA Approval Date | Date Site Confirmed By Sponsor | Date Site Confirmed | Non-Confirmation Status | Date Site Ready To Start | Reasons for Delay |  |  | Comments | Reasons for delay correspond to:
141813 | 18/NE/0077 | 235979 | PORT | No |  |  |  |  | 2018-02-06 | 2018-07-09 | 2018-05-31 |  |  | Please Select... |  | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
141814 | 17/LO/0980 | 219505 | HALT - Stereotactic Body Radiotherapy for the treatment of OPD | No |  | 90 |  |  | 2017-10-31 | 2018-07-13 | 2017-07-10 | 2018-10-09 | 2018-10-11 | Please Select... | 2018-12-14 | A - Permissions delayed/denied | H - Contracting delays | I - Rare diseases | A: Permissions Delayed: ARSAC Licence not received until 10/09/2018. H: Contracting Delays: Contract not receved from Sponsor until 11/10/2018. I: Rare diseases study: Condition being studied has an incidence of 9.7 per 100,000 fitting the EURORDIS definition. | Sponsor
141815 | 18/LO/0553 | 238522 | ECHO-208 | No |  |  |  |  | 2018-01-04 | 2018-07-17 | 2017-09-12 |  |  | Please Select... |  | C - Closed by sponsor |  |  | C: Study closed by the sponsor 29/10/2018, prior to confirmation. | Sponsor
141816 | 18/SC/0342 | 247085 | Phase III Trial of AMT-061 in adults with haemophilia B | Yes | 2019-01-03 | 136 | 31 | 167 | 2018-07-17 | 2018-07-20 | 2018-09-06 | 2018-12-03 | 2018-12-03 | Please Select... | 2019-01-03 | D - Sponsor Delays | H - Contracting delays |  | D: Sponsor delays: An amendment was submitted after site selected. Budget was not finalised by Sponsor until 01/11/2018. H: Contracting Delays: Final contract was not received from sponsor until 03/12/2018. | Sponsor
141817 | 18/LO/1187 | 240011 | ATHENA | No |  | 279 |  |  | 2018-06-11 | 2018-07-25 | 2018-09-11 | 2019-04-25 | 2019-04-30 | Please Select... | 2019-07-02 | D - Sponsor Delays | H - Contracting delays |  | D: Green Light Delayed: Sponsor greenlight not received until 02/07/2019. H: Contracting Delay: Contract not received back from the Sponsor until 30/04/2019 | Sponsor
141818 | 18/WM/0190 | 240027 | Combi-Aplus: Dabrafenib + Trametinib in BRAF+ve Melanoma | Yes | 2019-02-14 | 117 | 66 | 183 | 2018-05-02 | 2018-08-15 | 2018-08-09 | 2018-12-06 | 2018-12-10 | Please Select... | 2019-01-16 | D - Sponsor Delays | H - Contracting delays |  | H: Contracting delay: Sponsor did not return a signed contract until 10/12/2018 D: Sponsor Delay. Green light not given until 19/01/2019. | Sponsor
141819 | 18/SC/0364 | 248540 | RESTORE | Yes | 2018-10-15 | 41 | 19 | 60 | 2017-11-27 | 2018-08-16 | 2018-08-16 | 2018-09-26 | 2018-09-26 | Please Select... | 2018-09-26 |  |  |  | Met Target | Please Select...
141820 | 18/NW/0290 | 226529 | Phase 1/2 Multicentre open-label study of FT-2102 | No |  | 12 |  |  | 2018-07-20 | 2019-06-19 | 2018-06-20 | 2019-01-16 | 2019-07-01 | Please Select... | 2019-01-16 |  |  |  | Not yet passed 70 days since site selected. | Please Select...
141821 | 18/LO/0165 | 224726 | POLEM | No |  |  |  |  | 2018-04-27 | 2018-09-04 | 2018-05-09 |  |  | Please Select... |  | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
141822 | 18/EM/0269 | 250180 | Olaparib and abiraterone in metastatic prostate cancer | Yes | 2019-01-23 | 97 | 43 | 140 | 2018-08-08 | 2018-09-05 | 2018-11-13 | 2018-12-11 | 2018-12-11 | Please Select... | 2019-01-03 | A - Permissions delayed/denied | H - Contracting delays | I - Rare diseases | A: Permissions Delayed: ARSAC Licence not received until 14/11/2018. H: Contracting Delays: Contract not receved from Sponsor until 23/11/2018.I: Rare diseases study: Condition being studied has an incidence of 27 per 100,000 fitting the EURORDIS definition. | Sponsor
141823 | 18/SC/0429 | 247545 | Nivolumab and Relatlimab in first line gastric or GJ adenocarcinoma | No |  | 217 |  |  | 2018-05-10 | 2018-09-19 | 2018-11-22 | 2019-04-24 | 2019-04-24 | Please Select... | 2019-07-11 | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
141824 | 17/EE/0017 | 213606 | Investigating inhaled Promixin in the treatment of non-cystic fibrosis bronchiectasis | No |  | 7 |  |  | 2018-02-14 | 2018-11-07 | 2017-02-24 | 2018-10-22 | 2018-11-14 | Please Select... | 2018-11-27 | F - No patients seen |  |  | F: 49 potiential participants pre-screened but none eligible. | Neither
141825 | 18/SC/0254 | 244677 | iBiSS v1.0 | Yes | 2018-08-16 | 13 | 22 | 35 | 2018-04-10 | 2018-07-12 | 2018-07-12 | 2018-07-25 | 2018-07-25 | Please Select... | 2018-08-14 |  |  |  | Met Target | Please Select...
141826 | 18/LO/1192 | 248843 | SEAVUE - Safety and Efficacy of Adalimumab Vs Ustekinumab for one yEar | No |  | 7 |  |  | 2018-04-19 | 2018-10-02 | 2018-08-24 | 2018-10-10 | 2018-10-09 | Please Select... | 2018-10-10 | I - Rare diseases |  |  | I: Rare diseases study: Condition being studied has an incidence of 11.5 per 100,000 fitting the EURORDIS definition. | Neither
141827 | 18/LO/1311 | 248599 | GR40398 EFFICACY AND SAFETY OF RO6867461 IN DMO PATIENTS (RHINE) v1 | Yes | 2019-01-30 | 89 | 106 | 195 | 2018-06-07 | 2018-07-19 | 2018-10-03 | 2018-10-16 | 2018-10-16 | Please Select... | 2018-10-16 | D - Sponsor Delays | H - Contracting delays | I - Rare diseases | D: Sponsor Delay: Sponsor did not want to progress with Confirmation as they wanted to open in October. H: Contracting Delay: Contract not received until 10/10/2018. I: Rare diseases study: Condition being studied has an incidence of 46.9 per 100,000 fitting the EURORDIS definition. | Sponsor
141828 | 18/NE/0146 | 244849 | PTI-808-01 | No |  | 97 |  |  | 2018-02-22 | 2018-07-27 | 2018-07-26 | 2019-01-08 | 2018-11-01 | Please Select... | 2019-01-09 | D - Sponsor Delays | F - No patients seen | H - Contracting delays | D: Sponsor Delay: Sponsor did not confirm the site until 08/01/2019 and did not open the site to recruitment until 009/01/2019. H: Contracting Delays: Sponsor did not send contract until 26/10/2018 as they were not in a rush to open. F: Phase I study moving now to Phase II with chance to recruit in next cohort. | Sponsor
141829 | 18/YH/0219 | 242004 | Topaz | No |  |  |  |  | 2018-02-12 | 2018-08-06 | 2018-10-16 |  |  | Please Select... |  | C - Closed by sponsor |  |  | C: Study closed by sponsor 06/11/2018 prior to contract signature. | Sponsor
141830 | 18/WS/0102 | 230385 | Non-ionising diagnosis in Rheumatology , ECHO Bones project (ECHO-BONE) | Yes | 2019-01-04 | 70 | 17 | 87 | 2018-04-13 | 2018-10-09 | 2018-08-24 | 2018-12-18 | 2018-12-18 | Please Select... | 2018-12-18 | D - Sponsor Delays | F - No patients seen |  | D: Sponsor Delays: Final funding agreement not received bvy sponsor until 14/12/2018. F: 88 potiential participants pre-screened 1st participant now recruited. | Sponsor
141831 | 17/SC/0532 | 232887 | Inhaled SNG001 in COPD patients | Yes | 2018-11-06 | 15 | 41 | 56 | 2017-09-25 | 2018-09-11 | 2018-04-13 | 2018-09-18 | 2018-09-26 | Please Select... | 2018-10-04 |  |  |  | Met Target | Please Select...
141832 | 18/WM/0021 | 236090 | INTREPID: INvestigation of TRELEGY Effectiveness: Usual PractIce | Yes | 2018-11-05 | 1 | 39 | 40 | 2018-01-05 | 2018-09-26 | 2018-03-23 | 2018-09-18 | 2018-09-27 | Please Select... | 2018-10-09 |  |  |  | Met Target | Please Select...
141833 | 18/NE/0200 | 244356 | VX17-445-102 Efficacy and Safety of VX-445/TEZ/IVA in CF Het-min | Yes | 2018-10-12 | 0 | 14 | 14 | 2018-04-25 | 2018-09-28 | 2018-09-27 | 2018-09-28 | 2018-09-28 | Please Select... | 2018-09-28 |  |  |  | Met Target | Please Select...
141834 | 18/EE/0080 | 238897 | Tezidolid | No |  | 25 |  |  | 2018-01-03 | 2018-07-16 | 2018-05-30 | 2018-08-09 | 2018-08-10 | Please Select... | 2018-08-10 | C - Closed by sponsor |  |  | C: Study suspended by sponsor on 30/09/2018 and then it was subsequently closed. | Sponsor
141835 | 18/NE/0201 | 244419 | VX17-445-103 Efficacy and Safety of VX-445/TEZ/IVA in CF Homozygous | Yes | 2018-11-13 | 2 | 46 | 48 | 2018-02-23 | 2018-09-26 | 2019-09-27 | 2018-09-20 | 2018-09-28 | Please Select... | 2018-10-01 |  |  |  | Met Target | Please Select...
141836 | 18/SC/0384 | 245537 | VAC066 | Yes | 2018-12-12 | 24 | 13 | 37 | 2018-09-05 | 2018-11-05 | 2018-11-01 | 2018-11-29 | 2018-11-29 | Please Select... | 2018-11-29 |  |  |  | Met Target | Please Select...
141837 | 18/NS/0101 | 231097 | Preoxygenation with Optiflow - the effect of speech on oxygenation | Yes | 2018-10-18 | 9 | 7 | 16 | 2018-08-15 | 2018-10-02 | 2018-10-05 | 2018-10-11 | 2018-10-11 | Please Select... | 2018-10-11 |  |  |  | Met Target | Please Select...
141838 | 18/YH/0223 | 243476 | MET52 | Yes | 2019-02-06 | 10 | 104 | 114 | 2017-12-11 | 2018-10-15 | 2018-07-09 | 2018-10-18 | 2018-10-25 | Please Select... | 2018-12-18 | D - Sponsor Delays | F - No patients seen |  | D: Sponsor Delay. Green light to open for recruitment not given until 18/12/2018. F: No participants seen: Tight exclusion/inclusion criteria limited suitable presenting participants. | Sponsor
141839 | 18/NE/0172 | 247142 | ALLN-177 Pilot Study in patients with Enteric or Primary Hyperoxaluria | Yes | 2019-02-06 | 0 | 111 | 111 | 2018-06-13 | 2018-10-18 | 2018-08-31 | 2018-10-03 | 2018-10-18 | Please Select... | 2018-10-18 | I - Rare diseases |  |  | I: Rare diseases study: Condition being studied has an incidence of 0.2 per 100,000 fitting the NIHR definition. | Neither
141840 | 18/SC/0502 | 246134 | ACI-24-1801 | Yes | 2019-02-05 | 19 | 90 | 109 | 2018-03-26 | 2018-10-19 | 2018-10-15 | 2018-11-05 | 2018-11-07 | Please Select... | 2018-11-08 | D - Sponsor Delays |  |  | D: Sponsor closed screening for cohort 1 on 29/03/2019 as they have reached target. Screening suspended until sponsor confirms they are ready to begin cohort 2. | Sponsor
141841 | 18/SC/0396 | 235371 | The Let's Talk Early Labour (L-TEL) Trial | Yes | 2018-11-14 | 3 | 20 | 23 | 2018-05-23 | 2018-10-22 | 2018-10-15 | 2018-10-25 | 2018-10-25 | Please Select... | 2018-10-25 |  |  |  | Met Target | Please Select...
141842 | 18/WM/0204 | 244427 | VX17-445-105 Open-label Safety and Efficacy of VX-445/TEZ/IVA in CF | Yes | 2018-12-11 | 7 | 35 | 42 | 2018-02-23 | 2018-10-30 | 2018-10-18 | 2018-10-29 | 2018-11-06 | Please Select... | 2018-12-03 |  |  |  | Met Target | Please Select...
141843 | 17/LO/2068 | 216038 | RCT of RFA vs sham procedure for symptomatic cervical inlet patch | No |  | 30 |  |  | 2018-03-19 | 2018-11-12 | 2018-02-22 | 2018-12-12 | 2018-12-12 | Please Select... | 2018-12-12 | F - No patients seen |  |  | F: No eligible patients seen due to tight Inclusion/Exclusion criteria. Target recruitment of 2 in a year. | Neither
141844 | 18/LO/0330 | 236942 | Time Lapse Imaging Trial (TILT) | Yes | 2019-02-22 | 31 | 64 | 95 | 2018-07-06 | 2018-11-19 | 2018-05-25 | 2018-12-20 | 2018-12-20 | Please Select... | 2018-12-20 | F - No patients seen |  |  | F: 81 participants screened. First participant recruited 22/02/2019 | Neither
141845 | 16/NE/0008 | 170481 | I-KID: Infant KIdney Dialysis and filtration | Yes | 2019-01-22 | 0 | 54 | 54 | 2018-04-04 | 2018-11-29 | 2018-02-28 | 2018-11-09 | 2018-11-29 | Please Select... | 2018-11-29 |  |  |  | Met target. Last quarter HRA feedback stated Pre HRA it is a post HRA study. | Please Select...
141846 | 18/SC/0508 | 239069 | OCTOPus | Yes | 2019-03-21 | 35 | 70 | 105 | 2018-07-05 | 2018-12-06 | 2018-11-15 | 2019-01-10 | 2019-01-10 | Please Select... | 2019-01-11 | D - Sponsor Delays | F - No patients seen |  | D: Sponsor delay. Site confirmed by sponsor 10/01/2019 F: No Eligible patients seen: 101 patients screened and 6 recruited. Tight inclusion Exclusion criteria make the patient population rare. | Sponsor
141847 | 18/YH/0014 | 224065 | ACTIVE | Yes | 2019-02-26 | 23 | 55 | 78 | 2018-04-11 | 2018-12-10 | 2018-02-13 | 2018-12-19 | 2019-01-02 | Please Select... | 2019-01-02 | F - No patients seen |  |  | F: One eligible patient seen due to tight Inclusion/Exclusion criteria (Rare fracture). First patient seen 26/02/2019 | Neither
141848 | 18/SC/0421 | 247127 | M18-891 Phase 3 JAK monotherapy atopic dermatitis adolescents&adults | Yes | 2019-01-31 | 16 | 28 | 44 | 2018-05-10 | 2018-12-18 | 2018-10-17 | 2019-01-03 | 2019-01-03 | Please Select... | 2019-01-16 |  |  |  | Met target | Please Select...
141849 | 18/SS/0085 | 243640 | Alpha-2 agonists for sedation (A2B Trial) | Yes | 2019-04-18 | 24 | 97 | 121 | 2018-11-01 | 2018-12-18 | 2018-12-14 | 2018-12-20 | 2019-01-11 | Please Select... | 2019-01-14 | F - No patients seen |  |  | F: No eligible patients seen due to tight Inclusion/Exclusion criteria. Target recruitment of 2 in a year. 1st participant recruited on 18/04/2019. 130 participants screened. | Neither
141850 | 16/EE/0305 | 190307 | PRIMETIME | No |  | 174 |  |  | 2018-12-06 | 2019-01-03 | 2016-11-03 | 2019-06-17 | 2019-06-26 | Please Select... | 2019-06-27 | D - Sponsor Delays | F - No patients seen |  | D: Sponsor Delay: Confirmation from sponsor not received until 17/06/2019 and greenlight not given until 27/06/2019. F: No Eligible Patients seen: long screening period and 5 patients unergoing screening currently. | Sponsor
141851 | 17/YH/0311 | 229294 | A Modular, Multipart, Multiarm, FTiH, Open-label study of CT7001 | No |  |  |  |  | 2018-11-28 | 2019-01-03 | 2017-10-30 |  |  | Please Select... |  | D - Sponsor Delays |  |  | D: Sponsor Delay: Several amendments have been submitted after site selected which has slowed down study set-up. | Sponsor
141852 | 19/WA/0005 | 246081 | IP2 - ATLANTA | No |  | 61 |  |  | 2018-11-09 | 2019-05-22 | 2019-03-14 | 2019-07-22 | 2019-07-22 | Please Select... | 2019-07-22 |  |  |  | Study not passed 70 days since date site selected. | Please Select...
141853 | 19/NW/0004 | 248528 | RENAVIV | No |  |  |  |  | 2018-07-04 | 2019-01-10 |  |  |  | Please Select... |  | A - Permissions delayed/denied | B - Suspended by sponsor |  | A: Regulatory approvals not received: HRA approval still outstanding. B: Study set-up of new sites suspended by sponsor 17/06/2019. | Sponsor
141854 | 18/SC/0497 | 251148 | AGI-134 | No |  |  |  |  | 2018-06-12 | 2019-01-22 | 2019-01-28 |  |  | Site declined to participate |  |  |  |  | Site declined to participate. | Please Select...
141855 | 18/LO/2077 | 247401 | Pilot Study of Femtolaser Assisted Keratoplasty versus conventional keratoplasty | Yes | 2019-02-25 | 3 | 25 | 28 | 2018-07-10 | 2019-01-28 | 2019-01-28 | 2019-01-31 | 2019-01-31 | Please Select... | 2019-02-04 |  |  |  | Targets met | Please Select...
141856 | 13/EM/0015 | 118772 | NCRN546 - PCI-32765 (Ibrutinib) Long-term Extension Study | No |  | 73 |  |  | 2018-09-20 | 2019-04-29 | 2016-08-03 | 2019-07-10 | 2019-07-11 | Please Select... |  | D - Sponsor Delays | H - Contracting delays |  | D: Sponsor delay: Green light to start recruitment still awaited. H: Contracting delays: final contract not received from sponsor until 10/07/2019. | Sponsor
141857 | 18/LO/1359 | 231542 | IMPACT | No |  | 49 |  |  | 2018-07-31 | 2019-01-30 | 2019-01-07 | 2019-03-20 | 2019-03-20 | Please Select... | 2019-03-20 | F - No patients seen | J - Other |  | F: No eligible patients seen due to tight Inclusion/Exclusion criteria. Target recruitment of 5 in a year. J: Other: Unusual study design involving collaboration with another organisation to issue confirmatio of capcity and capability. | Neither
141858 | 18/EM/0112 | 236871 | ALL-RIC | No |  |  |  |  | 2018-05-01 | 2019-01-31 | 2018-06-12 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delays: final contract not received from sponsor yet | Sponsor
141859 | 18/WA/0417 | 251207 | AtTEnd | No |  |  |  |  | 2018-10-18 | 2019-01-31 | 2019-04-23 |  |  | Please Select... |  | A - Permissions delayed/denied | D - Sponsor Delays | H - Contracting delays | A: Regulatory approvals not received: HRA approval received 23/04/2019. D: Sponsor confirmation not yet received. H: Contracting delays: final contract not yet received from the Sponsor. | Sponsor
141860 | 18/NE/0223 | 249460 | XIENCE 28 | Yes | 2019-03-01 | 0 | 23 | 23 | 2018-05-01 | 2019-02-06 | 2018-09-26 | 2019-01-08 | 2019-02-06 | Please Select... | 2019-02-06 |  |  |  | Targets met | Please Select...
141861 | 18/NE/0296 | 248487 | CALIBRE Study | Yes | 2019-05-01 | 29 | 55 | 84 | 2018-12-05 | 2019-02-06 | 2018-10-19 | 2019-03-07 | 2019-03-07 | Please Select... | 2019-03-18 | F - No patients seen |  |  | F: 1st participant recruited. Tight participant Inclusion/Exclusion criteria. | Neither
141862 | 18/NE/0377 | 247077 | Southampton Arm Fracture Study | Yes | 2019-03-04 | 12 | 14 | 26 | 2018-10-24 | 2019-02-06 | 2018-12-12 | 2019-02-18 | 2019-02-18 | Please Select... | 2019-02-19 |  |  |  | Targets met | Please Select...
141863 | 18/SC/0682 | 254018 | Study of Tezepelumab in Moderate-to-Severe Atopic Dermatitis | No |  | 54 |  |  | 2018-10-15 | 2019-02-06 | 2018-12-11 | 2019-03-14 | 2019-04-01 | Please Select... | 2019-04-24 | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
141864 | 17/NW/0581 | 214739 | SC IL-1Ra in SAH - phase III trial | No |  |  |  |  | 2017-12-01 | 2019-02-07 | 2018-08-07 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delays: final contract not received from sponsor yet | Sponsor
141865 | 18/LO/0722 | 238635 | A Phase 3 study of Ozanimod as induction therapy for Crohns Disease | No |  | 39 |  |  | 2018-03-06 | 2019-02-07 | 2018-07-30 | 2019-03-18 | 2019-03-18 | Please Select... | 2019-06-07 | D - Sponsor Delays |  |  | D: Sponsor delay: Greenlight to open to recruitment not given until 07/06/2019. | Sponsor
141866 | 18/LO/0723 | 244615 | RPC01-3203:study of Ozanimod as Maintenance therapy for Crohns Disease | No |  | 39 |  |  | 2018-03-06 | 2019-02-07 | 2018-09-18 | 2019-03-18 | 2019-03-18 | Please Select... | 2019-06-07 | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
141867 | 18/NW/0105 | 239560 | LOCALIZE | Yes | 2019-04-18 | 3 | 62 | 65 | 2018-10-22 | 2019-02-12 | 2018-03-13 | 2019-02-01 | 2019-02-15 | Please Select... | 2019-02-15 |  |  |  | Targets met | Please Select...
141869 | 18/EE/0330 | 249125 | EASE SBS1 Efficacy And Safety Evaluation of Glepaglutide in SBS | No |  | 22 |  |  | 2018-05-10 | 2019-02-19 | 2018-12-11 | 2019-03-13 | 2019-03-13 | Please Select... | 2019-05-24 | I - Rare diseases |  |  | I: Rare Condition: Condition has an incidence of 1-9/100,000 fitting the EURORDIS definition of a rare disease. | Neither
141870 | 18/LO/1223 | 244752 | RPC01-3204: Open Label Extension study of Ozanimod for Crohn?s Disease | No |  | 25 |  |  | 2018-03-06 | 2019-02-25 | 2018-09-18 | 2019-03-22 | 2019-03-22 | Please Select... | 2019-06-07 | F - No patients seen |  |  | F: No Eligible Patients seen: Participants must be recruited into the main study before they can be recruited onto this follow-up study. | Neither
141871 | 17/EM/0077 | 206480 | LACI-2 | No |  | 1 |  |  | 2017-12-11 | 2019-02-26 | 2017-07-24 | 2018-04-01 | 2019-02-27 | Please Select... | 2019-05-31 | D - Sponsor Delays | F - No patients seen |  | D: Sponsor Dealy: Green light to open to recruitment not given unti 31/05/2019. F: No eligible patients seen: several patients screened but none are eligible. A few patients have also delcined to be screened for the study. | Sponsor
141872 | 18/WM/0383 | 252607 | Ecztra 7 (ECZema TRAlokinumab trial no. 7) | Yes | 2019-05-07 | 13 | 55 | 68 | 2018-08-30 | 2019-02-28 | 2019-02-06 | 2019-03-13 | 2019-03-13 | Please Select... | 2019-04-08 |  |  |  | Met Target | Please Select...
141873 | 18/LO/0543 | 242259 | Phase I/IIa study to evaluate CCS1477 in advanced tumours v1.0 | No |  |  |  |  | 2019-01-22 | 2019-03-05 | 2018-06-12 |  |  | Please Select... |  | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
141874 | 18/WA/0085 | 239967 | MS201781-0031, Phase 1b, open-label study in advanced solid tumours | No |  |  |  |  | 2017-12-21 | 2019-03-05 | 2018-06-08 |  |  | Please Select... |  | D - Sponsor Delays | H - Contracting delays |  | D: Sponsor delay: Protocol amendment submitted by the sponsor after site selected. H: Contracting delay: Final contract awaited from the Sponsor. | Sponsor
141875 | 18/NE/0142 | 242919 | The REVERSE study | No |  | 7 |  |  | 2018-12-28 | 2019-03-06 | 2018-07-13 | 2019-03-13 | 2019-03-13 | Please Select... | 2019-05-10 | F - No patients seen |  |  | F: 3 participants pre-screened and none eligible. 2 awaiting confirmation of eligibility (pre-screening phase). Difficult to find patients with FT4 for eligibility. | Neither
141876 | 18/YH/0477 | 253254 | A Phase 3 study of Zanubrutinib compared with Ibrutinib | No |  | 84 |  |  | 2018-12-14 | 2019-03-07 | 2019-01-23 | 2019-05-14 | 2019-05-30 | Please Select... | 2019-06-24 | D - Sponsor Delays |  |  | D: Delay with sponsor approving study costings. | Sponsor
141877 | 19/EM/0401 | 255615 | PARADIGM | No |  |  |  |  | 2019-01-22 | 2019-03-08 | 2019-04-15 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delay: Final contract awaited from the Sponsor. | Sponsor
141878 | 19/NI/0005 | 251129 | MOSAIC 014 | No |  | 65 |  |  | 2018-11-26 | 2019-05-14 | 2019-03-06 | 2019-07-18 | 2019-07-18 | Please Select... |  |  |  |  | Not yet passed 70 days since site selected. | Please Select...
141879 | 19/NW/0158 | 259931 | Surgery or Cast for Injuries of the EpicoNdyle in Children?s Elbows | No |  | 37 |  |  | 2019-02-07 | 2019-03-12 | 2019-03-25 | 2019-04-18 | 2019-04-18 | Please Select... | 2019-04-18 | I - Rare diseases |  |  | I: Rare injury approximately 12% of paediatric elbow injuries. | Neither
141880 | 18/SC/0420 | 235091 | Lyophilised Neisseria lactamica nasal challenge study | Yes | 2019-05-01 | 0 | 47 | 47 | 2018-08-06 | 2019-03-15 | 2018-10-08 | 2019-03-15 | 2019-03-15 | Please Select... | 2019-03-15 |  |  |  | Targets met | Please Select...
141881 | 18/YH/0392 | 252761 | GB001 in adult subjects with moderate to severe asthma | No |  | 11 |  |  | 2018-09-10 | 2019-03-15 | 2018-11-15 | 2019-03-26 | 2019-03-26 | Please Select... | 2019-05-14 | F - No patients seen |  |  | F: No Eligible Patients seen: 38 patients have unergone pre-screening and of them only 3 have gone forward for screening. Screening is currently underway for these 3 patients. | Neither
141882 | 18/EE/0347 | 232051 | A Single-dose Study of Tedizolid Phosphate in Pediatric Subjects < 2 Y | No |  | 31 |  |  | 2017-04-21 | 2019-03-18 | 2018-12-21 | 2019-04-18 | 2019-04-18 | Please Select... |  | D - Sponsor Delays |  |  | D: Sponsor Delays: Still awaiting sponsor green light to open to recruitment. | Sponsor
141883 | 18/LO/0745 | 231612 | IL-1 Signal Inhibition in Alcoholic Hepatitis (Isaiah) | No |  |  |  |  | 2018-11-21 | 2019-03-19 | 2018-07-11 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delays: final contract not received from sponsor yet | Sponsor
141884 | 18/LO/0508 | 241903 | A Follow-Up Study of Haemophilia B Patients after Gene Therapy | No |  | 29 |  |  | 2019-03-12 | 2019-03-20 | 2018-12-21 | 2019-04-18 | 2019-04-18 | Please Select... |  | D - Sponsor Delays |  |  | D: Sponsor Delays: Still awaiting sponsor green light to open to recruitment. | Sponsor
141885 | 19/SC/0172 | 256280 | EMERALD | No |  |  |  |  | 2019-01-31 | 2019-03-26 | 2019-06-07 |  |  | Please Select... |  | A - Permissions delayed/denied | D - Sponsor Delays |  | A: Regulatory Approvals not received: HRA approval not received until 07/06/2019. D: Sponsor delays: Sponsor submitted the local information pack before the Trust had said they would take part. | Sponsor
141886 | 19/EM/0047 | 257111 | GR40306 (TENAYA): A study of faricimab in nAMD | No |  | 60 |  |  | 2018-11-27 | 2019-03-29 | 2019-04-04 | 2019-05-28 | 2019-05-28 | Please Select... | 2019-07-02 | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
146439 | 19/EM/0028 | 254146 | PROTEUS | No |  |  |  |  | 2018-12-14 | 2019-04-02 | 2019-04-02 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delays: final contract not received from sponsor yet | Sponsor
146440 | 15/LO/1835 | 111728 | PNET 5 | No |  |  |  |  | 2016-06-16 | 2019-04-03 | 2016-10-20 |  |  | Please Select... |  | E - Staff availability issues |  |  | E: Staff Availability Issues: Temporary problems with staff availability in Trust pharmacy department. Issues being addressed by the management team. | NHS Provider
146441 | 16/EM/0322 | 202096 | Tenecteplase in Wake-up Ischaemic Stroke Trial (TWIST) | No |  |  |  |  | 2019-04-04 | 2019-04-04 | 2017-08-18 |  |  | Please Select... |  | D - Sponsor Delays |  |  | D: Sponsor Delay: Sponsor sent the local pack as a first contact with the Trust. Questions are outstanding and awaiting a response before the Trust decides if it can take part or not. | Sponsor
146442 | 17/LO/1808 | 231108 | ICON9 | No |  |  |  |  | 2019-03-01 | 2019-04-04 | 2017-12-18 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delays: final contract not received from sponsor yet | Sponsor
146443 | 18/LO/0324 | 220073 | VIDEO Trial: Vitrectomy In Diabetic macular Oedema Trial | No |  |  |  |  | 2018-11-20 | 2019-04-05 | 2018-04-03 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delays: final contract not received from sponsor yet. Funding shortage being negotiated. | Sponsor
146444 | 18/LO/1435 | 247443 | CHIRON ATX-NS-001 - ATL001 for the Treatment of Non-Small Cell Lung Cancer | No |  |  |  |  | 2018-06-25 | 2019-04-08 | 2019-04-25 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delay: Final contract not yet received from the sponsor. | Sponsor
146445 | 19/LO/0150 | 258058 | The EPITOPE Study | No |  | 65 |  |  | 2018-12-12 | 2019-04-09 | 2019-03-08 | 2019-05-15 | 2019-06-13 | Please Select... |  | E - Staff availability issues |  |  | D: Sponsor Delays: Still awaiting sponsor green light to open to recruitment. | Sponsor
146446 | 18/SC/0275 | 244088 | RADIcAL 1 | Yes | 2019-05-01 | 0 | 22 | 22 | 2018-09-06 | 2019-04-09 | 2018-06-08 | 2019-04-09 | 2019-04-09 | Please Select... | 2019-04-11 |  |  |  | Met target | Please Select...
146447 | 18/WM/0025 | 233804 | START:REACTS | No |  | 37 |  |  | 2018-09-28 | 2019-04-09 | 2018-02-13 | 2019-05-18 | 2019-05-16 | Please Select... | 2019-05-17 | F - No patients seen |  |  | F: No Eligible patients seen: Tight participant Inclusion/Exclusion criteria make the study population rare. | Neither
146448 | 18/NW/0699 | 241427 | TACE-3 | No |  |  |  |  | 2018-09-17 | 2019-04-16 | 2019-03-21 |  |  | Please Select... |  | H - Contracting delays |  |  | H: Contracting delays: final contract not received from sponsor yet | Sponsor
146449 | 18/WS/0120 | 245241 | PRISM (ACE-LY-111) | No |  |  |  |  | 2018-05-08 | 2019-04-22 | 2018-09-12 |  |  | Please Select... |  | E - Staff availability issues |  |  | Study not passed 70 days since date site selected. | Neither
146450 | 18/NW/0845 | 255810 | SMR-3438 | Yes | 2019-06-26 | 19 | 44 | 63 | 2018-09-10 | 2019-04-24 | 2019-04-18 | 2019-05-13 | 2019-05-13 | Please Select... | 2019-06-12 |  |  |  | Targets met | Please Select...
146451 | 19/LO/0546 | 250345 | Effectiveness and cost-effectiveness of inspiratory muscle training - INSPIRE | No |  |  |  |  | 2019-01-25 | 2019-04-24 | 2019-05-16 |  |  | Please Select... |  | D - Sponsor Delays |  |  | Study not passed 70 days since date site selected. | Neither
146452 | 18/YH/0358 | 242342 | The Sunflower Study | No |  |  |  |  | 2017-12-12 | 2019-05-01 | 2018-12-12 |  |  | Please Select... |  | D - Sponsor Delays |  |  | Study not passed 70 days since date site selected. | Neither
146453 | 19/YH/0144 | 256690 | Transconjunctival vs transcutaneous anaesthesia in oculoplastics | No |  | 28 |  |  | 2019-01-21 | 2019-05-07 | 2019-05-07 | 2019-06-04 | 2019-06-04 | Please Select... | 2019-06-04 |  |  |  | Not yet passed 70 days since site selected. | Please Select...
146454 | 19/NW/1606 | 257243 | Phase 2 study to evaluate PUR1900 in asthmatic patients with ABPA | No |  |  |  |  | 2019-01-11 | 2019-05-09 | 2019-04-15 |  |  | Please Select... |  | E - Staff availability issues |  |  | Study not passed 70 days since date site selected. | Neither
146455 | 19/LO/0167 | 259061 | iBaSS | Yes | 2019-07-15 | 5 | 61 | 66 | 2018-12-11 | 2019-05-10 | 2019-05-07 | 2019-05-15 | 2019-05-15 | Please Select... | 2019-06-27 |  |  |  | Met target | Please Select...
146456 | 18/LO/0555 | 237992 | PROTECTOR | Yes | 2019-07-15 | 27 | 35 | 62 | 2018-08-13 | 2019-05-14 | 2018-04-19 | 2019-06-10 | 2019-06-10 | Please Select... | 2019-06-27 |  |  |  | Met target | Please Select...
146457 | 18/LO/1937 | 249639 | Eribulin mesilate with irinotecan in children with solid tumours | No |  |  |  |  | 2018-05-07 | 2019-05-14 |  |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...
146458 | 19/SC/0031 | 257722 | RSV2002 Sero-negative toddlers vaccine study | No |  | 0 |  |  | 2018-01-17 | 2019-05-16 | 2019-04-10 | 2019-05-07 | 2019-05-16 | Please Select... | 2019-07-05 |  |  |  | Not yet passed 70 days since site selected. | Please Select...
146459 | 19/YH/0050 | 249236 | OpTIMUM | Yes | 2019-06-17 | 28 | 3 | 31 | 2019-03-01 | 2019-05-17 | 2019-03-28 | 2019-06-14 | 2019-06-14 | Please Select... | 2019-06-14 |  |  |  | Met target | Please Select...
146460 | 18/SC/0565 | 235717 | Naxitamab and GM-CSF in High Risk Neuroblastoma Patients v6.0 | No |  | 4 |  |  | 2018-06-07 | 2019-05-20 | 2013-08-05 | 2019-05-09 | 2019-05-24 | Please Select... |  |  |  |  | Not yet passed 70 days since site selected. | Please Select...
146461 | 19/LO/0879 | 264047 | Perioperative MK-3475 for cisplatin-ineligible patients with MIBC | No |  |  |  |  | 2019-01-02 | 2019-05-21 |  |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...
146462 | 18/EE/0356 | 250087 | NKTR-214 and Nivolumab in melanoma patients | No |  |  |  |  | 2018-08-01 | 2019-05-21 | 2019-01-25 |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...
146463 | 18/EE/0378 | 248600 | Conbercept in Neovascular Age-related Macular Degeneration | No |  |  |  |  | 2019-03-11 | 2019-05-22 | 2019-01-10 |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...
146464 | 18/NE/0246 | 242341 | Camstent Coated Foley Catheter | No |  | 23 |  |  | 2019-03-28 | 2019-05-22 | 2018-08-22 | 2019-06-14 | 2019-06-14 | Please Select... | 2019-07-11 |  |  |  | Not yet passed 70 days since site selected. | Please Select...
146465 | 19/HRA/2404 | 262048 | The TIRED-UK Study | Yes | 2019-06-28 | 0 | 31 | 31 | 2019-05-16 | 2019-05-28 | 2019-04-16 | 2019-05-28 | 2019-05-28 | Please Select... | 2019-05-30 |  |  |  | Met target | Please Select...
146466 | 18/WM/0077 | 239530 | CVAY736X2207 | No |  | 36 |  |  | 2018-12-21 | 2019-06-03 | 2018-05-03 | 2019-07-09 | 2019-07-09 | Please Select... |  |  |  |  | Not yet passed 70 days since site selected. | Please Select...
146467 | 19/LO/0533 | 255074 | HIT-CF Organoid Study | No |  |  |  |  | 2018-12-13 | 2019-06-07 | 2019-06-03 |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...
146468 | 19/SC/0312 | 263468 | GSK's paediatric HZ vaccine in paediatric renal transplant patients | No |  |  |  |  | 2019-03-07 | 2019-06-07 |  |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...
146469 | 19/SC/0221 | 259880 | Phase I/IIa study to evaluate CCS1477 in haem. malignancies v1.0 | No |  |  |  |  | 2019-01-22 | 2019-06-10 | 2019-06-10 |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...
146470 | 13/LO/1481 | 132746 | MARS 2 | No |  |  |  |  | 2018-11-29 | 2019-06-12 | 2016-10-28 |  |  | Please Select... |  | B - Suspended by sponsor |  |  | Study not passed 70 days since date site selected. | Neither
146471 | 17/SC/0610 | 227378 | iTIND RCT | No |  | 9 |  |  | 2018-01-10 | 2019-06-17 | 2017-12-08 | 2019-06-19 | 2019-06-26 | Please Select... |  |  |  |  | Not yet passed 70 days since site selected. | Please Select...
146472 | 19/NW/0442 | 262204 | JUVE BRIGHT | No |  |  |  |  | 2019-03-20 | 2019-06-20 |  |  |  | Please Select... |  |  |  |  | Study not passed 70 days since date site selected. | Please Select...